## transitions
building | category | month_index | year | month | period | from_state | to_state | transition_label | works_added | start_month | end_month | end_month_index | start_year | end_year | end_month_in_year | duration_months | cost | gain | is_instant
abri_bouliste | Sports | 218 | 2044 | 3 | 2044-03 | none | abri_bouliste_simulation_11 | none -> abri_bouliste_simulation_11 | indoor_wall_isolation, window_replacement_DG, floor_isolation, roof_isolation | 218 | 219 | 218 | 2044 | 2044 | 3 | 1 | 62094.12 | 6.0874 | FALSE
accueil_de_loisirs_maternel_la_varenne | Enseignement | 203 | 2042 | 12 | 2042-12 | none | accueil_de_loisirs_maternel_la_varenne_simulation_14 | none -> accueil_de_loisirs_maternel_la_varenne_simulation_14 | indoor_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation | 203 | 205 | 204 | 2042 | 2043 | 1 | 2 | 241467.9056 | 3.3198 | FALSE
association_31_rue_gambetta | Autres | 85 | 2033 | 2 | 2033-02 | none | association_31_rue_gambetta_simulation_6 | none -> association_31_rue_gambetta_simulation_6 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 85 | 87 | 86 | 2033 | 2033 | 3 | 2 | 167051.5 | 7.3257 | FALSE
ateliers_municipaux_(ctm) | Administration | 175 | 2040 | 8 | 2040-08 | none | ateliers_municipaux_(ctm)_simulation_7 | none -> ateliers_municipaux_(ctm)_simulation_7 | exterior_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation | 175 | 184 | 183 | 2040 | 2041 | 4 | 9 | 1981177.1 | 639.4242 | FALSE
ateliers_municipaux_(ctm) | Administration | 184 | 2041 | 5 | 2041-05 | ateliers_municipaux_(ctm)_simulation_7 | ateliers_municipaux_(ctm)_simulation_9 | ateliers_municipaux_(ctm)_simulation_7 -> ateliers_municipaux_(ctm)_simulation_9 | system_installation | 184 | 193 | 192 | 2041 | 2042 | 1 | 9 | 14380.36 | 36.46 | FALSE
base_de_canoe_kayak | Sports | 266 | 2048 | 3 | 2048-03 | none | base_de_canoe_kayak_simulation_12 | none -> base_de_canoe_kayak_simulation_12 | indoor_wall_isolation, floor_isolation, roof_isolation | 266 | 267 | 266 | 2048 | 2048 | 3 | 1 | 28031.7 | 13.6157 | FALSE
bureaux_21_rue_des_sports | Autres | 80 | 2032 | 9 | 2032-09 | none | bureaux_21_rue_des_sports_simulation_14 | none -> bureaux_21_rue_des_sports_simulation_14 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 80 | 81 | 80 | 2032 | 2032 | 9 | 1 | 43496.537 | 2.8605 | FALSE
cdj_du_champy | Autres | 284 | 2049 | 9 | 2049-09 | none | cdj_du_champy_simulation_8 | none -> cdj_du_champy_simulation_8 | indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation | 284 | 286 | 285 | 2049 | 2049 | 10 | 2 | 166570.6543 | 20.5543 | FALSE
cdj_du_pave_neuf | Autres | 94 | 2033 | 11 | 2033-11 | none | cdj_du_pave_neuf_simulation_1 | none -> cdj_du_pave_neuf_simulation_1 | indoor_wall_isolation | 94 | 96 | 95 | 2033 | 2033 | 12 | 2 | 26123.4895 | 9.0161 | FALSE
cdj_du_pave_neuf | Autres | 96 | 2034 | 1 | 2034-01 | cdj_du_pave_neuf_simulation_1 | cdj_du_pave_neuf_simulation_11 | cdj_du_pave_neuf_simulation_1 -> cdj_du_pave_neuf_simulation_11 | floor_isolation, roof_isolation, VMC_installation | 96 | 98 | 97 | 2034 | 2034 | 2 | 2 | 129716.6715 | 8.1772 | FALSE
centre_aquatique_les_nymphéas | Sports | 125 | 2036 | 6 | 2036-06 | none | centre_aquatique_les_nymphéas_simulation_1 | none -> centre_aquatique_les_nymphéas_simulation_1 | floor_isolation | 125 | 134 | 133 | 2036 | 2037 | 2 | 9 | 358316.0643 | 63.5966 | FALSE
centre_horticole | Administration | 254 | 2047 | 3 | 2047-03 | none | centre_horticole_simulation_15 | none -> centre_horticole_simulation_15 | exterior_wall_isolation, window_replacement_TG, roof_isolation | 254 | 256 | 255 | 2047 | 2047 | 4 | 2 | 183773.699 | 7.2991 | FALSE
cimetiere_nouveau | Autres | 143 | 2037 | 12 | 2037-12 | none | cimetiere_nouveau_simulation_9 | none -> cimetiere_nouveau_simulation_9 | floor_isolation | 143 | 144 | 143 | 2037 | 2037 | 12 | 1 | 6137.975 | 1.0522 | FALSE
cimetiere_nouveau | Autres | 144 | 2038 | 1 | 2038-01 | cimetiere_nouveau_simulation_9 | cimetiere_nouveau_simulation_11 | cimetiere_nouveau_simulation_9 -> cimetiere_nouveau_simulation_11 | indoor_wall_isolation, roof_isolation, VMC_installation | 144 | 145 | 144 | 2038 | 2038 | 1 | 1 | 33451.5635 | 5.6665 | FALSE
cinéma_le_bijou | Autres | 0 | 2026 | 1 | 2026-01 | none | cinéma_le_bijou_simulation_7 | none -> cinéma_le_bijou_simulation_7 | window_replacement_TG, floor_isolation, system_installation | 0 | 2 | 1 | 2026 | 2026 | 2 | 2 | 235081.83 | 195.5401 | FALSE
club_ricardo_bofil | Autres | 296 | 2050 | 9 | 2050-09 | none | club_ricardo_bofil_simulation_2 | none -> club_ricardo_bofil_simulation_2 | indoor_wall_isolation, floor_isolation | 296 | 300 | 299 | 2050 | 2050 | 12 | 4 | 169732.8639 | 3.2846 | FALSE
conservatoire_maurice_bacquet | Autres | 236 | 2045 | 9 | 2045-09 | none | conservatoire_maurice_bacquet_simulation 1 | none -> conservatoire_maurice_bacquet_simulation 1 | floor_isolation | 236 | 238 | 237 | 2045 | 2045 | 10 | 2 | 6776.8 | 0.095809 | FALSE
conservatoire_maurice_bacquet | Autres | 238 | 2045 | 11 | 2045-11 | conservatoire_maurice_bacquet_simulation 1 | conservatoire_maurice_bacquet_simulation 10 | conservatoire_maurice_bacquet_simulation 1 -> conservatoire_maurice_bacquet_simulation 10 | indoor_wall_isolation, VMC_installation, system_installation | 238 | 242 | 241 | 2045 | 2046 | 2 | 4 | 410659.34 | 37.2943 | FALSE
creche_multi_accueil_des_farfadets | Enseignement | 265 | 2048 | 2 | 2048-02 | none | creche_multi_accueil_des_farfadets_simulation_2 | none -> creche_multi_accueil_des_farfadets_simulation_2 | indoor_wall_isolation, floor_isolation | 265 | 267 | 266 | 2048 | 2048 | 3 | 2 | 96216.36 | 3.1962 | FALSE
crèche_et_halte_du_marnois | Enseignement | 222 | 2044 | 7 | 2044-07 | none | crèche_et_halte_du_marnois_simulation_5 | none -> crèche_et_halte_du_marnois_simulation_5 | VMC_installation | 222 | 222 | 221 | 2044 | 2044 | 6 | 0 | 149050 | 14.7649 | TRUE
crèche_et_halte_du_marnois | Enseignement | 222 | 2044 | 7 | 2044-07 | crèche_et_halte_du_marnois_simulation_5 | crèche_et_halte_du_marnois_simulation_10 | crèche_et_halte_du_marnois_simulation_5 -> crèche_et_halte_du_marnois_simulation_10 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 222 | 227 | 226 | 2044 | 2044 | 11 | 5 | 572346.2 | 68.7159 | FALSE
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | Enseignement | 199 | 2042 | 8 | 2042-08 | none | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | none -> crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | VMC_installation | 199 | 199 | 198 | 2042 | 2042 | 7 | 0 | 44686.0192 | 13.5994 | TRUE
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | Enseignement | 199 | 2042 | 8 | 2042-08 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_8 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 -> crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_8 | exterior_wall_isolation, window_replacement_DG, floor_isolation | 199 | 200 | 199 | 2042 | 2042 | 8 | 1 | 102613.9808 | 14.842 | FALSE
crèche_petit_prince | Enseignement | 12 | 2027 | 1 | 2027-01 | none | crèche_petit_prince_simulation_1 | none -> crèche_petit_prince_simulation_1 | exterior_wall_isolation | 12 | 16 | 15 | 2027 | 2027 | 4 | 4 | 190957 | 15.6779 | FALSE
crèche_petit_prince | Enseignement | 152 | 2038 | 9 | 2038-09 | crèche_petit_prince_simulation_1 | crèche_petit_prince_simulation_4 | crèche_petit_prince_simulation_1 -> crèche_petit_prince_simulation_4 | window_replacement_TG | 152 | 156 | 155 | 2038 | 2038 | 12 | 4 | 252737 | 20.661 | FALSE
crèche_robert_debré | Enseignement | 45 | 2029 | 10 | 2029-10 | none | crèche_robert_debré_simulation_6 | none -> crèche_robert_debré_simulation_6 | window_replacement_DG, roof_isolation, VMC_installation | 45 | 47 | 46 | 2029 | 2029 | 11 | 2 | 448044.37 | 52.5134 | FALSE
crèche_robert_debré | Enseignement | 74 | 2032 | 3 | 2032-03 | crèche_robert_debré_simulation_6 | crèche_robert_debré_simulation_10 | crèche_robert_debré_simulation_6 -> crèche_robert_debré_simulation_10 | indoor_wall_isolation, system_installation | 74 | 76 | 75 | 2032 | 2032 | 4 | 2 | 53621.44 | 12.8718 | FALSE
déchèterie_municipale | Administration | 59 | 2030 | 12 | 2030-12 | none | déchèterie_municipale_simulation_11 | none -> déchèterie_municipale_simulation_11 | indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation | 59 | 60 | 59 | 2030 | 2030 | 12 | 1 | 29536.9365 | 3.7791 | FALSE
emaus_1_et__2 | Autres | 138 | 2037 | 7 | 2037-07 | none | emaus_1_et__2_simulation_15 | none -> emaus_1_et__2_simulation_15 | indoor_wall_isolation, window_replacement_DG, floor_isolation, roof_isolation | 138 | 140 | 139 | 2037 | 2037 | 8 | 2 | 229094.3179 | 15.2374 | FALSE
espace_michel_simon | Autres | 47 | 2029 | 12 | 2029-12 | none | espace_michel_simon_simulation 4 | none -> espace_michel_simon_simulation 4 | window_replacement_DG | 47 | 56 | 55 | 2029 | 2030 | 8 | 9 | 1734957.675 | 356.1949 | FALSE
espace_michel_simon | Autres | 59 | 2030 | 12 | 2030-12 | espace_michel_simon_simulation 4 | espace_michel_simon_simulation 10 | espace_michel_simon_simulation 4 -> espace_michel_simon_simulation 10 | indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation | 59 | 70 | 69 | 2030 | 2031 | 10 | 11 | 2050105.395 | 441.0201 | FALSE
groupe_scolaire_des_hauts_bâtons | Enseignement | 181 | 2041 | 2 | 2041-02 | none | groupe_scolaire_des_hauts_bâtons_simulation_5 | none -> groupe_scolaire_des_hauts_bâtons_simulation_5 | system_installation | 181 | 181 | 180 | 2041 | 2041 | 1 | 0 | 35916.9205 | 47.5682 | TRUE
groupe_scolaire_des_hauts_bâtons | Enseignement | 278 | 2049 | 3 | 2049-03 | groupe_scolaire_des_hauts_bâtons_simulation_5 | groupe_scolaire_des_hauts_bâtons_simulation_7 | groupe_scolaire_des_hauts_bâtons_simulation_5 -> groupe_scolaire_des_hauts_bâtons_simulation_7 | exterior_wall_isolation, roof_isolation | 278 | 289 | 288 | 2049 | 2050 | 1 | 11 | 537306.864 | 195.4586 | FALSE
groupe_scolaire_les_coteaux | Enseignement | 225 | 2044 | 10 | 2044-10 | none | groupe_scolaire_les_coteaux_simulation_10 | none -> groupe_scolaire_les_coteaux_simulation_10 | exterior_wall_isolation, window_replacement_DG, VMC_installation | 225 | 234 | 233 | 2044 | 2045 | 6 | 9 | 1938960.808 | 367.7684 | FALSE
groupe_scolaire_les_richardets | Enseignement | 18 | 2027 | 7 | 2027-07 | none | groupe_scolaire_les_richardets_simulation_1 | none -> groupe_scolaire_les_richardets_simulation_1 | exterior_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation | 18 | 25 | 24 | 2027 | 2028 | 1 | 7 | 818360.552 | 328.6735 | FALSE
groupe_scolaire_paul_serelle | Enseignement | 293 | 2050 | 6 | 2050-06 | none | groupe_scolaire_paul_serelle_simulation_1 | none -> groupe_scolaire_paul_serelle_simulation_1 | exterior_wall_isolation, floor_isolation, roof_isolation | 293 | 300 | 299 | 2050 | 2050 | 12 | 7 | 573049.868 | 322.3713 | FALSE
groupe_scolaire_robert_desnos | Enseignement | 139 | 2037 | 8 | 2037-08 | none | groupe_scolaire_robert_desnos_simulation_8 | none -> groupe_scolaire_robert_desnos_simulation_8 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 139 | 147 | 146 | 2037 | 2038 | 3 | 8 | 838596 | 229.8409 | FALSE
groupe_scolaire_robert_desnos | Enseignement | 147 | 2038 | 4 | 2038-04 | groupe_scolaire_robert_desnos_simulation_8 | groupe_scolaire_robert_desnos_simulation_10 | groupe_scolaire_robert_desnos_simulation_8 -> groupe_scolaire_robert_desnos_simulation_10 | VMC_installation, system_installation | 147 | 155 | 154 | 2038 | 2038 | 11 | 8 | 311398.7981 | 10.2894 | FALSE
gs_alex_dumas | Enseignement | 34 | 2028 | 11 | 2028-11 | none | gs_alex_dumas_simulation 10 | none -> gs_alex_dumas_simulation 10 | exterior_wall_isolation, window_replacement_TG, VMC_installation, system_installation | 34 | 40 | 39 | 2028 | 2029 | 4 | 6 | 1396879.8 | 188.3802 | FALSE
gs_celestin_freinet | Enseignement | 77 | 2032 | 6 | 2032-06 | none | gs_celestin_freinet_simulation 10 | none -> gs_celestin_freinet_simulation 10 | indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation | 77 | 88 | 87 | 2032 | 2033 | 4 | 11 | 1671724.9125 | 307.6618 | FALSE
gs_clos_arche | Enseignement | 244 | 2046 | 5 | 2046-05 | none | gs_clos_arche_simulation 6 | none -> gs_clos_arche_simulation 6 | indoor_wall_isolation, window_replacement_DG | 244 | 251 | 250 | 2046 | 2046 | 11 | 7 | 589599.1625 | 109.2335 | FALSE
gs_clos_arche | Enseignement | 251 | 2046 | 12 | 2046-12 | gs_clos_arche_simulation 6 | gs_clos_arche_simulation 10 | gs_clos_arche_simulation 6 -> gs_clos_arche_simulation 10 | floor_isolation, VMC_installation, system_installation | 251 | 258 | 257 | 2046 | 2047 | 6 | 7 | 331155.7375 | 43.229 | FALSE
gs_clos_dambert | Enseignement | 0 | 2026 | 1 | 2026-01 | none | gs_clos_dambert_simulation 3 | none -> gs_clos_dambert_simulation 3 | window_replacement_DG | 0 | 5 | 4 | 2026 | 2026 | 5 | 5 | 968916.85 | 52.624 | FALSE
gs_clos_dambert | Enseignement | 153 | 2038 | 10 | 2038-10 | gs_clos_dambert_simulation 3 | gs_clos_dambert_simulation 7 | gs_clos_dambert_simulation 3 -> gs_clos_dambert_simulation 7 | VMC_installation | 153 | 158 | 157 | 2038 | 2039 | 2 | 5 | 576400 | 79.0263 | FALSE
gs_george_brassens | Enseignement | 234 | 2045 | 7 | 2045-07 | none | gs_george_brassens_simulation 8 | none -> gs_george_brassens_simulation 8 | exterior_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation | 234 | 241 | 240 | 2045 | 2046 | 1 | 7 | 1257984.63 | 270.3521 | FALSE
gs_joliot_curie | Enseignement | 83 | 2032 | 12 | 2032-12 | none | gs_joliot_curie_simulation 3 | none -> gs_joliot_curie_simulation 3 | system_installation | 83 | 83 | 82 | 2032 | 2032 | 11 | 0 | 79350 | 92.581 | TRUE
gs_joliot_curie | Enseignement | 196 | 2042 | 5 | 2042-05 | gs_joliot_curie_simulation 3 | gs_joliot_curie_simulation 9 | gs_joliot_curie_simulation 3 -> gs_joliot_curie_simulation 9 | exterior_wall_isolation, roof_isolation, VMC_installation | 196 | 205 | 204 | 2042 | 2043 | 1 | 9 | 1226589.325 | 636.9241 | FALSE
gs_jules_ferry | Enseignement | 114 | 2035 | 7 | 2035-07 | none | gs_jules_ferry_simulation 3 | none -> gs_jules_ferry_simulation 3 | window_replacement_TG | 114 | 120 | 119 | 2035 | 2035 | 12 | 6 | 1412174.0475 | 65.1233 | FALSE
gs_jules_ferry | Enseignement | 153 | 2038 | 10 | 2038-10 | gs_jules_ferry_simulation 3 | gs_jules_ferry_simulation 10 | gs_jules_ferry_simulation 3 -> gs_jules_ferry_simulation 10 | exterior_wall_isolation, floor_isolation, VMC_installation, system_installation | 153 | 164 | 163 | 2038 | 2039 | 8 | 11 | 1445442.1425 | 186.5038 | FALSE
gs_jules_verne | Enseignement | 88 | 2033 | 5 | 2033-05 | none | gs_jules_verne_simulation 10 | none -> gs_jules_verne_simulation 10 | exterior_wall_isolation, window_replacement_DG, floor_isolation, VMC_installation | 88 | 99 | 98 | 2033 | 2034 | 3 | 11 | 2331334.4 | 419.7526 | FALSE
gs_la_varenne | Enseignement | 165 | 2039 | 10 | 2039-10 | none | gs_la_varenne_simulation 3 | none -> gs_la_varenne_simulation 3 | window_replacement_TG | 165 | 172 | 171 | 2039 | 2040 | 4 | 7 | 1619959.2637 | 151.9269 | FALSE
gs_la_varenne | Enseignement | 187 | 2041 | 8 | 2041-08 | gs_la_varenne_simulation 3 | gs_la_varenne_simulation 10 | gs_la_varenne_simulation 3 -> gs_la_varenne_simulation 10 | exterior_wall_isolation, floor_isolation, system_installation | 187 | 200 | 199 | 2041 | 2042 | 8 | 13 | 759988.1063 | 232.0438 | FALSE
gs_les_abeilles | Enseignement | 274 | 2048 | 11 | 2048-11 | none | gs_les_abeilles_simulation 7 | none -> gs_les_abeilles_simulation 7 | system_installation | 274 | 274 | 273 | 2048 | 2048 | 10 | 0 | 29979.5 | 38.4436 | TRUE
gs_les_abeilles | Enseignement | 275 | 2048 | 12 | 2048-12 | gs_les_abeilles_simulation 7 | gs_les_abeilles_simulation 10 | gs_les_abeilles_simulation 7 -> gs_les_abeilles_simulation 10 | exterior_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation | 275 | 285 | 284 | 2048 | 2049 | 9 | 10 | 1637906.296 | 274.054 | FALSE
gs_les_charmilles | Enseignement | 129 | 2036 | 10 | 2036-10 | none | gs_les_charmilles_simulation 10 | none -> gs_les_charmilles_simulation 10 | indoor_wall_isolation, window_replacement_DG, VMC_installation | 129 | 135 | 134 | 2036 | 2037 | 3 | 6 | 736091.4 | 131.2078 | FALSE
gs_les_noyers | Enseignement | 117 | 2035 | 10 | 2035-10 | none | gs_les_noyers_simulation 10 | none -> gs_les_noyers_simulation 10 | indoor_wall_isolation, window_replacement_DG, roof_isolation, system_installation | 117 | 129 | 128 | 2035 | 2036 | 9 | 12 | 1799636.88 | 405.2362 | FALSE
gs_les_yvris | Enseignement | 6 | 2026 | 7 | 2026-07 | none | gs_les_yvris_simulation 5 | none -> gs_les_yvris_simulation 5 | VMC_installation | 6 | 6 | 5 | 2026 | 2026 | 6 | 0 | 445300 | 66.0893 | TRUE
gs_les_yvris | Enseignement | 6 | 2026 | 7 | 2026-07 | gs_les_yvris_simulation 5 | gs_les_yvris_simulation 10 | gs_les_yvris_simulation 5 -> gs_les_yvris_simulation 10 | exterior_wall_isolation, window_replacement_TG | 6 | 13 | 12 | 2026 | 2027 | 1 | 7 | 1245925.8 | 242.2328 | FALSE
gs_van_gogh | Enseignement | 16 | 2027 | 5 | 2027-05 | none | gs_van_gogh_simulation 10 | none -> gs_van_gogh_simulation 10 | exterior_wall_isolation, window_replacement_DG, roof_isolation, system_installation | 16 | 26 | 25 | 2027 | 2028 | 2 | 10 | 1313775.26 | 214.2346 | FALSE
gymnase_champy | Sports | 214 | 2043 | 11 | 2043-11 | none | gymnase_champy_simulation 8 | none -> gymnase_champy_simulation 8 | VMC_installation, system_installation | 214 | 214 | 213 | 2043 | 2043 | 10 | 0 | 272250.12 | 123.8419 | TRUE
gymnase_champy | Sports | 214 | 2043 | 11 | 2043-11 | gymnase_champy_simulation 8 | gymnase_champy_simulation 10 | gymnase_champy_simulation 8 -> gymnase_champy_simulation 10 | exterior_wall_isolation, window_replacement_TG | 214 | 219 | 218 | 2043 | 2044 | 3 | 5 | 644591.3 | 15.5084 | FALSE
gymnase_de_la_butte_verte | Sports | 255 | 2047 | 4 | 2047-04 | none | gymnase_de_la_butte_verte_simulation_5 | none -> gymnase_de_la_butte_verte_simulation_5 | window_replacement_DG, system_installation | 255 | 262 | 261 | 2047 | 2047 | 10 | 7 | 1364168.78 | 183.2757 | FALSE
gymnase_du_clos_de_l'arche | Sports | 264 | 2048 | 1 | 2048-01 | none | gymnase_du_clos_de_l'arche_simulation_2 | none -> gymnase_du_clos_de_l'arche_simulation_2 | window_replacement_TG | 264 | 267 | 266 | 2048 | 2048 | 3 | 3 | 569215.2 | 14.8578 | FALSE
gymnase_la_varenne | Sports | 78 | 2032 | 7 | 2032-07 | none | gymnase_la_varenne_simulation 10 | none -> gymnase_la_varenne_simulation 10 | window_replacement_DG, VMC_installation, system_installation | 78 | 81 | 80 | 2032 | 2032 | 9 | 3 | 837193.7 | 143.0206 | FALSE
gymnase_les_coteaux | Sports | 131 | 2036 | 12 | 2036-12 | none | gymnase_les_coteaux_simulation_3 | none -> gymnase_les_coteaux_simulation_3 | window_replacement_DG | 131 | 132 | 131 | 2036 | 2036 | 12 | 1 | 211318.8 | 9.0681 | FALSE
gymnase_les_coteaux | Sports | 193 | 2042 | 2 | 2042-02 | gymnase_les_coteaux_simulation_3 | gymnase_les_coteaux_simulation_9 | gymnase_les_coteaux_simulation_3 -> gymnase_les_coteaux_simulation_9 | indoor_wall_isolation, VMC_installation | 193 | 196 | 195 | 2042 | 2042 | 4 | 3 | 175382.4 | 21.1737 | FALSE
gymnase_les_yvris | Sports | 148 | 2038 | 5 | 2038-05 | none | gymnase_les_yvris_simulation_6 | none -> gymnase_les_yvris_simulation_6 | VMC_installation | 148 | 148 | 147 | 2038 | 2038 | 4 | 0 | 185150 | 80.9724 | TRUE
gymnase_les_yvris | Sports | 191 | 2041 | 12 | 2041-12 | gymnase_les_yvris_simulation_6 | gymnase_les_yvris_simulation_10 | gymnase_les_yvris_simulation_6 -> gymnase_les_yvris_simulation_10 | indoor_wall_isolation, roof_isolation, system_installation | 191 | 196 | 195 | 2041 | 2042 | 4 | 5 | 228918.85 | 96.2766 | FALSE
gymnase_louison_bobet | Sports | 155 | 2038 | 12 | 2038-12 | none | gymnase_louison_bobet_simulation 4 | none -> gymnase_louison_bobet_simulation 4 | system_installation | 155 | 155 | 154 | 2038 | 2038 | 11 | 0 | 12166.8 | 25.0785 | TRUE
gymnase_louison_bobet | Sports | 206 | 2043 | 3 | 2043-03 | gymnase_louison_bobet_simulation 4 | gymnase_louison_bobet_simulation 6 | gymnase_louison_bobet_simulation 4 -> gymnase_louison_bobet_simulation 6 | exterior_wall_isolation | 206 | 215 | 214 | 2043 | 2043 | 11 | 9 | 413800.2 | 75.3924 | FALSE
gymnase_louison_bobet | Sports | 291 | 2050 | 4 | 2050-04 | gymnase_louison_bobet_simulation 6 | gymnase_louison_bobet_simulation 10 | gymnase_louison_bobet_simulation 6 -> gymnase_louison_bobet_simulation 10 | roof_isolation, VMC_installation | 291 | 300 | 299 | 2050 | 2050 | 12 | 9 | 394782.2 | 101.5067 | FALSE
hangar_bleu | Autres | 57 | 2030 | 10 | 2030-10 | none | hangar_bleu_simulation_9 | none -> hangar_bleu_simulation_9 | indoor_wall_isolation, floor_isolation, roof_isolation, system_installation | 57 | 61 | 60 | 2030 | 2031 | 1 | 4 | 333898.7334 | 83.6049 | FALSE
local_associatif_pablo_picasso | Autres | 43 | 2029 | 8 | 2029-08 | none | local_associatif_pablo_picasso_simulation_15 | none -> local_associatif_pablo_picasso_simulation_15 | window_replacement_DG | 43 | 44 | 43 | 2029 | 2029 | 8 | 1 | 48137.6663 | 0.25867 | FALSE
local_associatif_pablo_picasso | Autres | 232 | 2045 | 5 | 2045-05 | local_associatif_pablo_picasso_simulation_15 | local_associatif_pablo_picasso_simulation_7 | local_associatif_pablo_picasso_simulation_15 -> local_associatif_pablo_picasso_simulation_7 | indoor_wall_isolation, floor_isolation | 232 | 233 | 232 | 2045 | 2045 | 5 | 1 | 23087.7635 | 0.79411 | FALSE
maison_de_la_jeunesse | Autres | 58 | 2030 | 11 | 2030-11 | none | maison_de_la_jeunesse_simulation_1 | none -> maison_de_la_jeunesse_simulation_1 | indoor_wall_isolation | 58 | 59 | 58 | 2030 | 2030 | 11 | 1 | 15402.11 | 5.0858 | FALSE
maison_de_la_jeunesse | Autres | 59 | 2030 | 12 | 2030-12 | maison_de_la_jeunesse_simulation_1 | maison_de_la_jeunesse_simulation_8 | maison_de_la_jeunesse_simulation_1 -> maison_de_la_jeunesse_simulation_8 | roof_isolation | 59 | 60 | 59 | 2030 | 2030 | 12 | 1 | 23085.21 | 2.6942 | FALSE
maison_de_la_jeunesse | Autres | 60 | 2031 | 1 | 2031-01 | maison_de_la_jeunesse_simulation_8 | maison_de_la_jeunesse_simulation_10 | maison_de_la_jeunesse_simulation_8 -> maison_de_la_jeunesse_simulation_10 | floor_isolation | 60 | 61 | 60 | 2031 | 2031 | 1 | 1 | 8690.9 | 1.3463 | FALSE
maison_de_la_jeunesse | Autres | 61 | 2031 | 2 | 2031-02 | maison_de_la_jeunesse_simulation_10 | maison_de_la_jeunesse_simulation_9 | maison_de_la_jeunesse_simulation_10 -> maison_de_la_jeunesse_simulation_9 | VMC_installation | 61 | 62 | 61 | 2031 | 2031 | 2 | 1 | 13253.62 | 2.8473 | FALSE
maison_des_services_publics_-_pimms | Administration | 131 | 2036 | 12 | 2036-12 | none | maison_des_services_publics_-_pimms_simulation_13 | none -> maison_des_services_publics_-_pimms_simulation_13 | indoor_wall_isolation, window_replacement_DG, floor_isolation, VMC_installation | 131 | 133 | 132 | 2036 | 2037 | 1 | 2 | 191635.7399 | 17.5558 | FALSE
maison_des_syndicats | Autres | 18 | 2027 | 7 | 2027-07 | none | maison_des_syndicats_simulation_13 | none -> maison_des_syndicats_simulation_13 | indoor_wall_isolation, roof_isolation | 18 | 19 | 18 | 2027 | 2027 | 7 | 1 | 74612.91 | 1.7875 | FALSE
maison_des_syndicats | Autres | 19 | 2027 | 8 | 2027-08 | maison_des_syndicats_simulation_13 | maison_des_syndicats_simulation_11 | maison_des_syndicats_simulation_13 -> maison_des_syndicats_simulation_11 | window_replacement_TG | 19 | 20 | 19 | 2027 | 2027 | 8 | 1 | 104460.79 | 2.5779 | FALSE
maison_medicale_du_champy | Autres | 197 | 2042 | 6 | 2042-06 | none | maison_medicale_du_champy_simulation_3 | none -> maison_medicale_du_champy_simulation_3 | floor_isolation | 197 | 198 | 197 | 2042 | 2042 | 6 | 1 | 39297.2201 | 2.4155 | FALSE
maison_medicale_du_champy | Autres | 198 | 2042 | 7 | 2042-07 | maison_medicale_du_champy_simulation_3 | maison_medicale_du_champy_simulation_14 | maison_medicale_du_champy_simulation_3 -> maison_medicale_du_champy_simulation_14 | exterior_wall_isolation, window_replacement_DG, VMC_installation | 198 | 199 | 198 | 2042 | 2042 | 7 | 1 | 252680.1334 | 7.9089 | FALSE
medecine_du_travail | Administration | 169 | 2040 | 2 | 2040-02 | none | medecine_du_travail_simulation_9 | none -> medecine_du_travail_simulation_9 | VMC_installation | 169 | 169 | 168 | 2040 | 2040 | 1 | 0 | 26560.8063 | 2.2639 | TRUE
medecine_du_travail | Administration | 194 | 2042 | 3 | 2042-03 | medecine_du_travail_simulation_9 | medecine_du_travail_simulation_3 | medecine_du_travail_simulation_9 -> medecine_du_travail_simulation_3 | indoor_wall_isolation | 194 | 196 | 195 | 2042 | 2042 | 4 | 2 | 28412.7881 | 4.5821 | FALSE
medecine_du_travail | Administration | 227 | 2044 | 12 | 2044-12 | medecine_du_travail_simulation_3 | medecine_du_travail_simulation_8 | medecine_du_travail_simulation_3 -> medecine_du_travail_simulation_8 | floor_isolation, roof_isolation | 227 | 229 | 228 | 2044 | 2045 | 1 | 2 | 71935.517 | 4.0602 | FALSE
mille_club_des_yvris | Autres | 222 | 2044 | 7 | 2044-07 | none | mille_club_des_yvris_simulation_6 | none -> mille_club_des_yvris_simulation_6 | floor_isolation, roof_isolation | 222 | 223 | 222 | 2044 | 2044 | 7 | 1 | 60083.4216 | 3.8751 | FALSE
mille_club_des_yvris | Autres | 223 | 2044 | 8 | 2044-08 | mille_club_des_yvris_simulation_6 | mille_club_des_yvris_simulation_7 | mille_club_des_yvris_simulation_6 -> mille_club_des_yvris_simulation_7 | indoor_wall_isolation, window_replacement_DG | 223 | 224 | 223 | 2044 | 2044 | 8 | 1 | 103387.5886 | 5.3258 | FALSE
mpt_des_coteaux | Autres | 196 | 2042 | 5 | 2042-05 | none | mpt_des_coteaux_simulation_1 | none -> mpt_des_coteaux_simulation_1 | floor_isolation | 196 | 197 | 196 | 2042 | 2042 | 5 | 1 | 18257.6825 | 3.4 | FALSE
mpt_des_coteaux | Autres | 198 | 2042 | 7 | 2042-07 | mpt_des_coteaux_simulation_1 | mpt_des_coteaux_simulation_13 | mpt_des_coteaux_simulation_1 -> mpt_des_coteaux_simulation_13 | exterior_wall_isolation, window_replacement_DG, roof_isolation | 198 | 200 | 199 | 2042 | 2042 | 8 | 2 | 184237.0895 | 14.608 | FALSE
mpt_du_champy | Autres | 264 | 2048 | 1 | 2048-01 | none | mpt_du_champy_simulation_9 | none -> mpt_du_champy_simulation_9 | indoor_wall_isolation, window_replacement_TG, system_installation | 264 | 265 | 264 | 2048 | 2048 | 1 | 1 | 436518.336 | 35.537 | FALSE
mpt_du_champy | Autres | 299 | 2050 | 12 | 2050-12 | mpt_du_champy_simulation_9 | mpt_du_champy_simulation_10 | mpt_du_champy_simulation_9 -> mpt_du_champy_simulation_10 | VMC_installation | 299 | 300 | 299 | 2050 | 2050 | 12 | 1 | 92033.116 | 0.1403 | FALSE
mpt_jardin_des_sources_-_annexe_maison_pour_tous | Autres | 294 | 2050 | 7 | 2050-07 | none | mpt_jardin_des_sources_-_annexe_maison_pour_tous_simulation_3 | none -> mpt_jardin_des_sources_-_annexe_maison_pour_tous_simulation_3 | exterior_wall_isolation, floor_isolation | 294 | 298 | 297 | 2050 | 2050 | 10 | 4 | 243402.9467 | 5.6227 | FALSE
mpt_la_varenne | Autres | 71 | 2031 | 12 | 2031-12 | none | mpt_la_varenne_simulation 10 | none -> mpt_la_varenne_simulation 10 | indoor_wall_isolation, window_replacement_TG, roof_isolation, VMC_installation, system_installation | 71 | 73 | 72 | 2031 | 2032 | 1 | 2 | 293752.19 | 59.5504 | FALSE
mpt_les_richardets | Autres | 260 | 2047 | 9 | 2047-09 | none | mpt_les_richardets_simulation_6 | none -> mpt_les_richardets_simulation_6 | indoor_wall_isolation, roof_isolation | 260 | 263 | 262 | 2047 | 2047 | 11 | 3 | 100666.7 | 3.6246 | FALSE
mpt_les_richardets | Autres | 263 | 2047 | 12 | 2047-12 | mpt_les_richardets_simulation_6 | mpt_les_richardets_simulation_10 | mpt_les_richardets_simulation_6 -> mpt_les_richardets_simulation_10 | window_replacement_DG, VMC_installation | 263 | 266 | 265 | 2047 | 2048 | 2 | 3 | 229990.7 | 17.9809 | FALSE
mpt_marcel_bou | Autres | 111 | 2035 | 4 | 2035-04 | none | mpt_marcel_bou_simulation 7 | none -> mpt_marcel_bou_simulation 7 | VMC_installation | 111 | 111 | 110 | 2035 | 2035 | 3 | 0 | 13250 | 6.1706 | TRUE
mpt_marcel_bou | Autres | 111 | 2035 | 4 | 2035-04 | mpt_marcel_bou_simulation 7 | mpt_marcel_bou_simulation 10 | mpt_marcel_bou_simulation 7 -> mpt_marcel_bou_simulation 10 | indoor_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation, system_installation | 111 | 113 | 112 | 2035 | 2035 | 5 | 2 | 212061.14 | 42.2159 | FALSE
multi_accueil_jean_piaget | Enseignement | 181 | 2041 | 2 | 2041-02 | none | multi_accueil_jean_piaget_simulation_4 | none -> multi_accueil_jean_piaget_simulation_4 | VMC_installation | 181 | 181 | 180 | 2041 | 2041 | 1 | 0 | 157570.4552 | 21.1429 | TRUE
multi_accueil_jean_piaget | Enseignement | 279 | 2049 | 4 | 2049-04 | multi_accueil_jean_piaget_simulation_4 | multi_accueil_jean_piaget_simulation_7 | multi_accueil_jean_piaget_simulation_4 -> multi_accueil_jean_piaget_simulation_7 | indoor_wall_isolation, window_replacement_DG, floor_isolation | 279 | 282 | 281 | 2049 | 2049 | 6 | 3 | 316840.8906 | 64.6613 | FALSE
noisy_connecte | Autres | 7 | 2026 | 8 | 2026-08 | none | noisy_connecte_simulation_9 | none -> noisy_connecte_simulation_9 | indoor_wall_isolation, window_replacement_TG, floor_isolation | 7 | 8 | 7 | 2026 | 2026 | 8 | 1 | 37602 | 10.5922 | FALSE
salle_de_boxe | Sports | 0 | 2026 | 1 | 2026-01 | none | salle_de_boxe_simulation_5 | none -> salle_de_boxe_simulation_5 | indoor_wall_isolation, floor_isolation, VMC_installation | 0 | 1 | 0 | 2026 | 2026 | 1 | 1 | 52159.1257 | 13.4249 | FALSE
salle_polyvalente_stephan_hessel | Autres | 130 | 2036 | 11 | 2036-11 | none | salle_polyvalente_stephan_hessel_simulation_7 | none -> salle_polyvalente_stephan_hessel_simulation_7 | indoor_wall_isolation, window_replacement_TG, floor_isolation | 130 | 131 | 130 | 2036 | 2036 | 11 | 1 | 82956.2132 | 7.386 | FALSE
stade_alain_mimoun | Sports | 264 | 2048 | 1 | 2048-01 | none | stade_alain_mimoun_simulation_10 | none -> stade_alain_mimoun_simulation_10 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 264 | 267 | 266 | 2048 | 2048 | 3 | 3 | 258349.6 | 83.437 | FALSE
stade_municipal_des_bords_de_marne | Sports | 141 | 2037 | 10 | 2037-10 | none | stade_municipal_des_bords_de_marne_simulation_10 | none -> stade_municipal_des_bords_de_marne_simulation_10 | indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation | 141 | 144 | 143 | 2037 | 2037 | 12 | 3 | 540906.7577 | 95.3312 | FALSE
stade_suzanne_lenglen | Sports | 20 | 2027 | 9 | 2027-09 | none | stade_suzanne_lenglen_simulation_10 | none -> stade_suzanne_lenglen_simulation_10 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 20 | 22 | 21 | 2027 | 2027 | 10 | 2 | 157359.1 | 26.2298 | FALSE
tir_a_l'arc | Sports | 82 | 2032 | 11 | 2032-11 | none | tir_a_l'arc_simulation_14 | none -> tir_a_l'arc_simulation_14 | indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation | 82 | 84 | 83 | 2032 | 2032 | 12 | 2 | 412750.4 | 13.647 | FALSE
villa_cathala | Autres | 167 | 2039 | 12 | 2039-12 | none | villa_cathala_simulation 2 | none -> villa_cathala_simulation 2 | indoor_wall_isolation | 167 | 169 | 168 | 2039 | 2040 | 1 | 2 | 48034.2 | 41.6582 | FALSE
villa_cathala | Autres | 170 | 2040 | 3 | 2040-03 | villa_cathala_simulation 2 | villa_cathala_simulation 10 | villa_cathala_simulation 2 -> villa_cathala_simulation 10 | window_replacement_TG, VMC_installation | 170 | 172 | 171 | 2040 | 2040 | 4 | 2 | 237403.9 | 13.1698 | FALSE

## timeline_renovations
building | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11 | 2027-12 | 2028-01 | 2028-02 | 2028-03 | 2028-04 | 2028-05 | 2028-06 | 2028-07 | 2028-08 | 2028-09 | 2028-10 | 2028-11 | 2028-12 | 2029-01 | 2029-02 | 2029-03 | 2029-04 | 2029-05 | 2029-06 | 2029-07 | 2029-08 | 2029-09 | 2029-10 | 2029-11 | 2029-12 | 2030-01 | 2030-02 | 2030-03 | 2030-04 | 2030-05 | 2030-06 | 2030-07 | 2030-08 | 2030-09 | 2030-10 | 2030-11 | 2030-12 | 2031-01 | 2031-02 | 2031-03 | 2031-04 | 2031-05 | 2031-06 | 2031-07 | 2031-08 | 2031-09 | 2031-10 | 2031-11 | 2031-12 | 2032-01 | 2032-02 | 2032-03 | 2032-04 | 2032-05 | 2032-06 | 2032-07 | 2032-08 | 2032-09 | 2032-10 | 2032-11 | 2032-12 | 2033-01 | 2033-02 | 2033-03 | 2033-04 | 2033-05 | 2033-06 | 2033-07 | 2033-08 | 2033-09 | 2033-10 | 2033-11 | 2033-12 | 2034-01 | 2034-02 | 2034-03 | 2034-04 | 2034-05 | 2034-06 | 2034-07 | 2034-08 | 2034-09 | 2034-10 | 2034-11 | 2034-12 | 2035-01 | 2035-02 | 2035-03 | 2035-04 | 2035-05 | 2035-06 | 2035-07 | 2035-08 | 2035-09 | 2035-10 | 2035-11 | 2035-12 | 2036-01 | 2036-02 | 2036-03 | 2036-04 | 2036-05 | 2036-06 | 2036-07 | 2036-08 | 2036-09 | 2036-10 | 2036-11 | 2036-12 | 2037-01 | 2037-02 | 2037-03 | 2037-04 | 2037-05 | 2037-06 | 2037-07 | 2037-08 | 2037-09 | 2037-10 | 2037-11 | 2037-12 | 2038-01 | 2038-02 | 2038-03 | 2038-04 | 2038-05 | 2038-06 | 2038-07 | 2038-08 | 2038-09 | 2038-10 | 2038-11 | 2038-12 | 2039-01 | 2039-02 | 2039-03 | 2039-04 | 2039-05 | 2039-06 | 2039-07 | 2039-08 | 2039-09 | 2039-10 | 2039-11 | 2039-12 | 2040-01 | 2040-02 | 2040-03 | 2040-04 | 2040-05 | 2040-06 | 2040-07 | 2040-08 | 2040-09 | 2040-10 | 2040-11 | 2040-12 | 2041-01 | 2041-02 | 2041-03 | 2041-04 | 2041-05 | 2041-06 | 2041-07 | 2041-08 | 2041-09 | 2041-10 | 2041-11 | 2041-12 | 2042-01 | 2042-02 | 2042-03 | 2042-04 | 2042-05 | 2042-06 | 2042-07 | 2042-08 | 2042-09 | 2042-10 | 2042-11 | 2042-12 | 2043-01 | 2043-02 | 2043-03 | 2043-04 | 2043-05 | 2043-06 | 2043-07 | 2043-08 | 2043-09 | 2043-10 | 2043-11 | 2043-12 | 2044-01 | 2044-02 | 2044-03 | 2044-04 | 2044-05 | 2044-06 | 2044-07 | 2044-08 | 2044-09 | 2044-10 | 2044-11 | 2044-12 | 2045-01 | 2045-02 | 2045-03 | 2045-04 | 2045-05 | 2045-06 | 2045-07 | 2045-08 | 2045-09 | 2045-10 | 2045-11 | 2045-12 | 2046-01 | 2046-02 | 2046-03 | 2046-04 | 2046-05 | 2046-06 | 2046-07 | 2046-08 | 2046-09 | 2046-10 | 2046-11 | 2046-12 | 2047-01 | 2047-02 | 2047-03 | 2047-04 | 2047-05 | 2047-06 | 2047-07 | 2047-08 | 2047-09 | 2047-10 | 2047-11 | 2047-12 | 2048-01 | 2048-02 | 2048-03 | 2048-04 | 2048-05 | 2048-06 | 2048-07 | 2048-08 | 2048-09 | 2048-10 | 2048-11 | 2048-12 | 2049-01 | 2049-02 | 2049-03 | 2049-04 | 2049-05 | 2049-06 | 2049-07 | 2049-08 | 2049-09 | 2049-10 | 2049-11 | 2049-12 | 2050-01 | 2050-02 | 2050-03 | 2050-04 | 2050-05 | 2050-06 | 2050-07 | 2050-08 | 2050-09 | 2050-10 | 2050-11 | 2050-12
abri_bouliste | 2044-03: none -> abri_bouliste_simulation_11
accueil_de_loisirs_maternel_la_varenne | 2042-12: none -> accueil_de_loisirs_maternel_la_varenne_simulation_14
association_31_rue_gambetta | 2033-02: none -> association_31_rue_gambetta_simulation_6
ateliers_municipaux_(ctm) | 2040-08: none -> ateliers_municipaux_(ctm)_simulation_7; 2041-05: ateliers_municipaux_(ctm)_simulation_7 -> ateliers_municipaux_(ctm)_simulation_9
base_de_canoe_kayak | 2048-03: none -> base_de_canoe_kayak_simulation_12
bureaux_21_rue_des_sports | 2032-09: none -> bureaux_21_rue_des_sports_simulation_14
cdj_du_champy | 2049-09: none -> cdj_du_champy_simulation_8
cdj_du_pave_neuf | 2033-11: none -> cdj_du_pave_neuf_simulation_1; 2034-01: cdj_du_pave_neuf_simulation_1 -> cdj_du_pave_neuf_simulation_11
centre_aquatique_les_nymphéas | 2036-06: none -> centre_aquatique_les_nymphéas_simulation_1
centre_horticole | 2047-03: none -> centre_horticole_simulation_15
cimetiere_nouveau | 2037-12: none -> cimetiere_nouveau_simulation_9; 2038-01: cimetiere_nouveau_simulation_9 -> cimetiere_nouveau_simulation_11
cinéma_le_bijou | 2026-01: none -> cinéma_le_bijou_simulation_7
club_ricardo_bofil | 2050-09: none -> club_ricardo_bofil_simulation_2
conservatoire_maurice_bacquet | 2045-09: none -> conservatoire_maurice_bacquet_simulation 1; 2045-11: conservatoire_maurice_bacquet_simulation 1 -> conservatoire_maurice_bacquet_simulation 10
creche_multi_accueil_des_farfadets | 2048-02: none -> creche_multi_accueil_des_farfadets_simulation_2
crèche_et_halte_du_marnois | 2044-07: none -> crèche_et_halte_du_marnois_simulation_5
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2042-08: none -> crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4
crèche_petit_prince | 2027-01: none -> crèche_petit_prince_simulation_1; 2038-09: crèche_petit_prince_simulation_1 -> crèche_petit_prince_simulation_4
crèche_robert_debré | 2029-10: none -> crèche_robert_debré_simulation_6; 2032-03: crèche_robert_debré_simulation_6 -> crèche_robert_debré_simulation_10
déchèterie_municipale | 2030-12: none -> déchèterie_municipale_simulation_11
emaus_1_et__2 | 2037-07: none -> emaus_1_et__2_simulation_15
espace_michel_simon | 2029-12: none -> espace_michel_simon_simulation 4; 2030-12: espace_michel_simon_simulation 4 -> espace_michel_simon_simulation 10
groupe_scolaire_des_hauts_bâtons | 2041-02: none -> groupe_scolaire_des_hauts_bâtons_simulation_5; 2049-03: groupe_scolaire_des_hauts_bâtons_simulation_5 -> groupe_scolaire_des_hauts_bâtons_simulation_7
groupe_scolaire_les_coteaux | 2044-10: none -> groupe_scolaire_les_coteaux_simulation_10
groupe_scolaire_les_richardets | 2027-07: none -> groupe_scolaire_les_richardets_simulation_1
groupe_scolaire_paul_serelle | 2050-06: none -> groupe_scolaire_paul_serelle_simulation_1
groupe_scolaire_robert_desnos | 2037-08: none -> groupe_scolaire_robert_desnos_simulation_8; 2038-04: groupe_scolaire_robert_desnos_simulation_8 -> groupe_scolaire_robert_desnos_simulation_10
gs_alex_dumas | 2028-11: none -> gs_alex_dumas_simulation 10
gs_celestin_freinet | 2032-06: none -> gs_celestin_freinet_simulation 10
gs_clos_arche | 2046-05: none -> gs_clos_arche_simulation 6; 2046-12: gs_clos_arche_simulation 6 -> gs_clos_arche_simulation 10
gs_clos_dambert | 2026-01: none -> gs_clos_dambert_simulation 3; 2038-10: gs_clos_dambert_simulation 3 -> gs_clos_dambert_simulation 7
gs_george_brassens | 2045-07: none -> gs_george_brassens_simulation 8
gs_joliot_curie | 2032-12: none -> gs_joliot_curie_simulation 3; 2042-05: gs_joliot_curie_simulation 3 -> gs_joliot_curie_simulation 9
gs_jules_ferry | 2035-07: none -> gs_jules_ferry_simulation 3; 2038-10: gs_jules_ferry_simulation 3 -> gs_jules_ferry_simulation 10
gs_jules_verne | 2033-05: none -> gs_jules_verne_simulation 10
gs_la_varenne | 2039-10: none -> gs_la_varenne_simulation 3; 2041-08: gs_la_varenne_simulation 3 -> gs_la_varenne_simulation 10
gs_les_abeilles | 2048-11: none -> gs_les_abeilles_simulation 7; 2048-12: gs_les_abeilles_simulation 7 -> gs_les_abeilles_simulation 10
gs_les_charmilles | 2036-10: none -> gs_les_charmilles_simulation 10
gs_les_noyers | 2035-10: none -> gs_les_noyers_simulation 10
gs_les_yvris | 2026-07: none -> gs_les_yvris_simulation 5
gs_van_gogh | 2027-05: none -> gs_van_gogh_simulation 10
gymnase_champy | 2043-11: none -> gymnase_champy_simulation 8
gymnase_de_la_butte_verte | 2047-04: none -> gymnase_de_la_butte_verte_simulation_5
gymnase_du_clos_de_l'arche | 2048-01: none -> gymnase_du_clos_de_l'arche_simulation_2
gymnase_la_varenne | 2032-07: none -> gymnase_la_varenne_simulation 10
gymnase_les_coteaux | 2036-12: none -> gymnase_les_coteaux_simulation_3; 2042-02: gymnase_les_coteaux_simulation_3 -> gymnase_les_coteaux_simulation_9
gymnase_les_yvris | 2038-05: none -> gymnase_les_yvris_simulation_6; 2041-12: gymnase_les_yvris_simulation_6 -> gymnase_les_yvris_simulation_10
gymnase_louison_bobet | 2038-12: none -> gymnase_louison_bobet_simulation 4; 2043-03: gymnase_louison_bobet_simulation 4 -> gymnase_louison_bobet_simulation 6; 2050-04: gymnase_louison_bobet_simulation 6 -> gymnase_louison_bobet_simulation 10
hangar_bleu | 2030-10: none -> hangar_bleu_simulation_9
local_associatif_pablo_picasso | 2029-08: none -> local_associatif_pablo_picasso_simulation_15; 2045-05: local_associatif_pablo_picasso_simulation_15 -> local_associatif_pablo_picasso_simulation_7
maison_de_la_jeunesse | 2030-11: none -> maison_de_la_jeunesse_simulation_1; 2030-12: maison_de_la_jeunesse_simulation_1 -> maison_de_la_jeunesse_simulation_8; 2031-01: maison_de_la_jeunesse_simulation_8 -> maison_de_la_jeunesse_simulation_10; 2031-02: maison_de_la_jeunesse_simulation_10 -> maison_de_la_jeunesse_simulation_9
maison_des_services_publics_-_pimms | 2036-12: none -> maison_des_services_publics_-_pimms_simulation_13
maison_des_syndicats | 2027-07: none -> maison_des_syndicats_simulation_13; 2027-08: maison_des_syndicats_simulation_13 -> maison_des_syndicats_simulation_11
maison_medicale_du_champy | 2042-06: none -> maison_medicale_du_champy_simulation_3; 2042-07: maison_medicale_du_champy_simulation_3 -> maison_medicale_du_champy_simulation_14
medecine_du_travail | 2040-02: none -> medecine_du_travail_simulation_9; 2042-03: medecine_du_travail_simulation_9 -> medecine_du_travail_simulation_3; 2044-12: medecine_du_travail_simulation_3 -> medecine_du_travail_simulation_8
mille_club_des_yvris | 2044-07: none -> mille_club_des_yvris_simulation_6; 2044-08: mille_club_des_yvris_simulation_6 -> mille_club_des_yvris_simulation_7
mpt_des_coteaux | 2042-05: none -> mpt_des_coteaux_simulation_1; 2042-07: mpt_des_coteaux_simulation_1 -> mpt_des_coteaux_simulation_13
mpt_du_champy | 2048-01: none -> mpt_du_champy_simulation_9; 2050-12: mpt_du_champy_simulation_9 -> mpt_du_champy_simulation_10
mpt_jardin_des_sources_-_annexe_maison_pour_tous | 2050-07: none -> mpt_jardin_des_sources_-_annexe_maison_pour_tous_simulation_3
mpt_la_varenne | 2031-12: none -> mpt_la_varenne_simulation 10
mpt_les_richardets | 2047-09: none -> mpt_les_richardets_simulation_6; 2047-12: mpt_les_richardets_simulation_6 -> mpt_les_richardets_simulation_10
mpt_marcel_bou | 2035-04: none -> mpt_marcel_bou_simulation 7
multi_accueil_jean_piaget | 2041-02: none -> multi_accueil_jean_piaget_simulation_4; 2049-04: multi_accueil_jean_piaget_simulation_4 -> multi_accueil_jean_piaget_simulation_7
noisy_connecte | 2026-08: none -> noisy_connecte_simulation_9
salle_de_boxe | 2026-01: none -> salle_de_boxe_simulation_5
salle_polyvalente_stephan_hessel | 2036-11: none -> salle_polyvalente_stephan_hessel_simulation_7
stade_alain_mimoun | 2048-01: none -> stade_alain_mimoun_simulation_10
stade_municipal_des_bords_de_marne | 2037-10: none -> stade_municipal_des_bords_de_marne_simulation_10
stade_suzanne_lenglen | 2027-09: none -> stade_suzanne_lenglen_simulation_10
tir_a_l'arc | 2032-11: none -> tir_a_l'arc_simulation_14
villa_cathala | 2039-12: none -> villa_cathala_simulation 2; 2040-03: villa_cathala_simulation 2 -> villa_cathala_simulation 10

## timeline_travaux
building | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11 | 2027-12 | 2028-01 | 2028-02 | 2028-03 | 2028-04 | 2028-05 | 2028-06 | 2028-07 | 2028-08 | 2028-09 | 2028-10 | 2028-11 | 2028-12 | 2029-01 | 2029-02 | 2029-03 | 2029-04 | 2029-05 | 2029-06 | 2029-07 | 2029-08 | 2029-09 | 2029-10 | 2029-11 | 2029-12 | 2030-01 | 2030-02 | 2030-03 | 2030-04 | 2030-05 | 2030-06 | 2030-07 | 2030-08 | 2030-09 | 2030-10 | 2030-11 | 2030-12 | 2031-01 | 2031-02 | 2031-03 | 2031-04 | 2031-05 | 2031-06 | 2031-07 | 2031-08 | 2031-09 | 2031-10 | 2031-11 | 2031-12 | 2032-01 | 2032-02 | 2032-03 | 2032-04 | 2032-05 | 2032-06 | 2032-07 | 2032-08 | 2032-09 | 2032-10 | 2032-11 | 2032-12 | 2033-01 | 2033-02 | 2033-03 | 2033-04 | 2033-05 | 2033-06 | 2033-07 | 2033-08 | 2033-09 | 2033-10 | 2033-11 | 2033-12 | 2034-01 | 2034-02 | 2034-03 | 2034-04 | 2034-05 | 2034-06 | 2034-07 | 2034-08 | 2034-09 | 2034-10 | 2034-11 | 2034-12 | 2035-01 | 2035-02 | 2035-03 | 2035-04 | 2035-05 | 2035-06 | 2035-07 | 2035-08 | 2035-09 | 2035-10 | 2035-11 | 2035-12 | 2036-01 | 2036-02 | 2036-03 | 2036-04 | 2036-05 | 2036-06 | 2036-07 | 2036-08 | 2036-09 | 2036-10 | 2036-11 | 2036-12 | 2037-01 | 2037-02 | 2037-03 | 2037-04 | 2037-05 | 2037-06 | 2037-07 | 2037-08 | 2037-09 | 2037-10 | 2037-11 | 2037-12 | 2038-01 | 2038-02 | 2038-03 | 2038-04 | 2038-05 | 2038-06 | 2038-07 | 2038-08 | 2038-09 | 2038-10 | 2038-11 | 2038-12 | 2039-01 | 2039-02 | 2039-03 | 2039-04 | 2039-05 | 2039-06 | 2039-07 | 2039-08 | 2039-09 | 2039-10 | 2039-11 | 2039-12 | 2040-01 | 2040-02 | 2040-03 | 2040-04 | 2040-05 | 2040-06 | 2040-07 | 2040-08 | 2040-09 | 2040-10 | 2040-11 | 2040-12 | 2041-01 | 2041-02 | 2041-03 | 2041-04 | 2041-05 | 2041-06 | 2041-07 | 2041-08 | 2041-09 | 2041-10 | 2041-11 | 2041-12 | 2042-01 | 2042-02 | 2042-03 | 2042-04 | 2042-05 | 2042-06 | 2042-07 | 2042-08 | 2042-09 | 2042-10 | 2042-11 | 2042-12 | 2043-01 | 2043-02 | 2043-03 | 2043-04 | 2043-05 | 2043-06 | 2043-07 | 2043-08 | 2043-09 | 2043-10 | 2043-11 | 2043-12 | 2044-01 | 2044-02 | 2044-03 | 2044-04 | 2044-05 | 2044-06 | 2044-07 | 2044-08 | 2044-09 | 2044-10 | 2044-11 | 2044-12 | 2045-01 | 2045-02 | 2045-03 | 2045-04 | 2045-05 | 2045-06 | 2045-07 | 2045-08 | 2045-09 | 2045-10 | 2045-11 | 2045-12 | 2046-01 | 2046-02 | 2046-03 | 2046-04 | 2046-05 | 2046-06 | 2046-07 | 2046-08 | 2046-09 | 2046-10 | 2046-11 | 2046-12 | 2047-01 | 2047-02 | 2047-03 | 2047-04 | 2047-05 | 2047-06 | 2047-07 | 2047-08 | 2047-09 | 2047-10 | 2047-11 | 2047-12 | 2048-01 | 2048-02 | 2048-03 | 2048-04 | 2048-05 | 2048-06 | 2048-07 | 2048-08 | 2048-09 | 2048-10 | 2048-11 | 2048-12 | 2049-01 | 2049-02 | 2049-03 | 2049-04 | 2049-05 | 2049-06 | 2049-07 | 2049-08 | 2049-09 | 2049-10 | 2049-11 | 2049-12 | 2050-01 | 2050-02 | 2050-03 | 2050-04 | 2050-05 | 2050-06 | 2050-07 | 2050-08 | 2050-09 | 2050-10 | 2050-11 | 2050-12
abri_bouliste | 2044-03: indoor_wall_isolation, window_replacement_DG, floor_isolation, roof_isolation
accueil_de_loisirs_maternel_la_varenne | 2042-12: indoor_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation
association_31_rue_gambetta | 2033-02: indoor_wall_isolation, window_replacement_DG, roof_isolation
ateliers_municipaux_(ctm) | 2040-08: exterior_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation; 2041-05: system_installation
base_de_canoe_kayak | 2048-03: indoor_wall_isolation, floor_isolation, roof_isolation
bureaux_21_rue_des_sports | 2032-09: indoor_wall_isolation, window_replacement_DG, roof_isolation
cdj_du_champy | 2049-09: indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation
cdj_du_pave_neuf | 2033-11: indoor_wall_isolation; 2034-01: floor_isolation, roof_isolation, VMC_installation
centre_aquatique_les_nymphéas | 2036-06: floor_isolation
centre_horticole | 2047-03: exterior_wall_isolation, window_replacement_TG, roof_isolation
cimetiere_nouveau | 2037-12: floor_isolation; 2038-01: indoor_wall_isolation, roof_isolation, VMC_installation
cinéma_le_bijou | 2026-01: window_replacement_TG, floor_isolation, system_installation
club_ricardo_bofil | 2050-09: indoor_wall_isolation, floor_isolation
conservatoire_maurice_bacquet | 2045-09: floor_isolation; 2045-11: indoor_wall_isolation, VMC_installation, system_installation
creche_multi_accueil_des_farfadets | 2048-02: indoor_wall_isolation, floor_isolation
crèche_et_halte_du_marnois | 2044-07: VMC_installation ¦ indoor_wall_isolation, window_replacement_DG, roof_isolation
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2042-08: VMC_installation ¦ exterior_wall_isolation, window_replacement_DG, floor_isolation
crèche_petit_prince | 2027-01: exterior_wall_isolation; 2038-09: window_replacement_TG
crèche_robert_debré | 2029-10: window_replacement_DG, roof_isolation, VMC_installation; 2032-03: indoor_wall_isolation, system_installation
déchèterie_municipale | 2030-12: indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation
emaus_1_et__2 | 2037-07: indoor_wall_isolation, window_replacement_DG, floor_isolation, roof_isolation
espace_michel_simon | 2029-12: window_replacement_DG; 2030-12: indoor_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation
groupe_scolaire_des_hauts_bâtons | 2041-02: system_installation; 2049-03: exterior_wall_isolation, roof_isolation
groupe_scolaire_les_coteaux | 2044-10: exterior_wall_isolation, window_replacement_DG, VMC_installation
groupe_scolaire_les_richardets | 2027-07: exterior_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation
groupe_scolaire_paul_serelle | 2050-06: exterior_wall_isolation, floor_isolation, roof_isolation
groupe_scolaire_robert_desnos | 2037-08: indoor_wall_isolation, window_replacement_DG, roof_isolation; 2038-04: VMC_installation, system_installation
gs_alex_dumas | 2028-11: exterior_wall_isolation, window_replacement_TG, VMC_installation, system_installation
gs_celestin_freinet | 2032-06: indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation
gs_clos_arche | 2046-05: indoor_wall_isolation, window_replacement_DG; 2046-12: floor_isolation, VMC_installation, system_installation
gs_clos_dambert | 2026-01: window_replacement_DG; 2038-10: VMC_installation
gs_george_brassens | 2045-07: exterior_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation
gs_joliot_curie | 2032-12: system_installation; 2042-05: exterior_wall_isolation, roof_isolation, VMC_installation
gs_jules_ferry | 2035-07: window_replacement_TG; 2038-10: exterior_wall_isolation, floor_isolation, VMC_installation, system_installation
gs_jules_verne | 2033-05: exterior_wall_isolation, window_replacement_DG, floor_isolation, VMC_installation
gs_la_varenne | 2039-10: window_replacement_TG; 2041-08: exterior_wall_isolation, floor_isolation, system_installation
gs_les_abeilles | 2048-11: system_installation; 2048-12: exterior_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation
gs_les_charmilles | 2036-10: indoor_wall_isolation, window_replacement_DG, VMC_installation
gs_les_noyers | 2035-10: indoor_wall_isolation, window_replacement_DG, roof_isolation, system_installation
gs_les_yvris | 2026-07: VMC_installation ¦ exterior_wall_isolation, window_replacement_TG
gs_van_gogh | 2027-05: exterior_wall_isolation, window_replacement_DG, roof_isolation, system_installation
gymnase_champy | 2043-11: VMC_installation, system_installation ¦ exterior_wall_isolation, window_replacement_TG
gymnase_de_la_butte_verte | 2047-04: window_replacement_DG, system_installation
gymnase_du_clos_de_l'arche | 2048-01: window_replacement_TG
gymnase_la_varenne | 2032-07: window_replacement_DG, VMC_installation, system_installation
gymnase_les_coteaux | 2036-12: window_replacement_DG; 2042-02: indoor_wall_isolation, VMC_installation
gymnase_les_yvris | 2038-05: VMC_installation; 2041-12: indoor_wall_isolation, roof_isolation, system_installation
gymnase_louison_bobet | 2038-12: system_installation; 2043-03: exterior_wall_isolation; 2050-04: roof_isolation, VMC_installation
hangar_bleu | 2030-10: indoor_wall_isolation, floor_isolation, roof_isolation, system_installation
local_associatif_pablo_picasso | 2029-08: window_replacement_DG; 2045-05: indoor_wall_isolation, floor_isolation
maison_de_la_jeunesse | 2030-11: indoor_wall_isolation; 2030-12: roof_isolation; 2031-01: floor_isolation; 2031-02: VMC_installation
maison_des_services_publics_-_pimms | 2036-12: indoor_wall_isolation, window_replacement_DG, floor_isolation, VMC_installation
maison_des_syndicats | 2027-07: indoor_wall_isolation, roof_isolation; 2027-08: window_replacement_TG
maison_medicale_du_champy | 2042-06: floor_isolation; 2042-07: exterior_wall_isolation, window_replacement_DG, VMC_installation
medecine_du_travail | 2040-02: VMC_installation; 2042-03: indoor_wall_isolation; 2044-12: floor_isolation, roof_isolation
mille_club_des_yvris | 2044-07: floor_isolation, roof_isolation; 2044-08: indoor_wall_isolation, window_replacement_DG
mpt_des_coteaux | 2042-05: floor_isolation; 2042-07: exterior_wall_isolation, window_replacement_DG, roof_isolation
mpt_du_champy | 2048-01: indoor_wall_isolation, window_replacement_TG, system_installation; 2050-12: VMC_installation
mpt_jardin_des_sources_-_annexe_maison_pour_tous | 2050-07: exterior_wall_isolation, floor_isolation
mpt_la_varenne | 2031-12: indoor_wall_isolation, window_replacement_TG, roof_isolation, VMC_installation, system_installation
mpt_les_richardets | 2047-09: indoor_wall_isolation, roof_isolation; 2047-12: window_replacement_DG, VMC_installation
mpt_marcel_bou | 2035-04: VMC_installation ¦ indoor_wall_isolation, window_replacement_TG, floor_isolation, roof_isolation, system_installation
multi_accueil_jean_piaget | 2041-02: VMC_installation; 2049-04: indoor_wall_isolation, window_replacement_DG, floor_isolation
noisy_connecte | 2026-08: indoor_wall_isolation, window_replacement_TG, floor_isolation
salle_de_boxe | 2026-01: indoor_wall_isolation, floor_isolation, VMC_installation
salle_polyvalente_stephan_hessel | 2036-11: indoor_wall_isolation, window_replacement_TG, floor_isolation
stade_alain_mimoun | 2048-01: indoor_wall_isolation, window_replacement_DG, roof_isolation
stade_municipal_des_bords_de_marne | 2037-10: indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation
stade_suzanne_lenglen | 2027-09: indoor_wall_isolation, window_replacement_DG, roof_isolation
tir_a_l'arc | 2032-11: indoor_wall_isolation, window_replacement_DG, roof_isolation, VMC_installation
villa_cathala | 2039-12: indoor_wall_isolation; 2040-03: window_replacement_TG, VMC_installation

## stats_mois
year | month | period | renovations_started | cost_total_started | renovations_instant
2026 | 1 | 2026-01 | 3 | 1256157.8057 | 0
2026 | 2 | 2026-02 | 0 | 0 | 0
2026 | 3 | 2026-03 | 0 | 0 | 0
2026 | 4 | 2026-04 | 0 | 0 | 0
2026 | 5 | 2026-05 | 0 | 0 | 0
2026 | 6 | 2026-06 | 0 | 0 | 0
2026 | 7 | 2026-07 | 2 | 1691225.8 | 1
2026 | 8 | 2026-08 | 1 | 37602 | 0
2026 | 9 | 2026-09 | 0 | 0 | 0
2026 | 10 | 2026-10 | 0 | 0 | 0
2026 | 11 | 2026-11 | 0 | 0 | 0
2026 | 12 | 2026-12 | 0 | 0 | 0
2027 | 1 | 2027-01 | 1 | 190957 | 0
2027 | 2 | 2027-02 | 0 | 0 | 0
2027 | 3 | 2027-03 | 0 | 0 | 0
2027 | 4 | 2027-04 | 0 | 0 | 0
2027 | 5 | 2027-05 | 1 | 1313775.26 | 0
2027 | 6 | 2027-06 | 0 | 0 | 0
2027 | 7 | 2027-07 | 2 | 892973.462 | 0
2027 | 8 | 2027-08 | 1 | 104460.79 | 0
2027 | 9 | 2027-09 | 1 | 157359.1 | 0
2027 | 10 | 2027-10 | 0 | 0 | 0
2027 | 11 | 2027-11 | 0 | 0 | 0
2027 | 12 | 2027-12 | 0 | 0 | 0
2028 | 1 | 2028-01 | 0 | 0 | 0
2028 | 2 | 2028-02 | 0 | 0 | 0
2028 | 3 | 2028-03 | 0 | 0 | 0
2028 | 4 | 2028-04 | 0 | 0 | 0
2028 | 5 | 2028-05 | 0 | 0 | 0
2028 | 6 | 2028-06 | 0 | 0 | 0
2028 | 7 | 2028-07 | 0 | 0 | 0
2028 | 8 | 2028-08 | 0 | 0 | 0
2028 | 9 | 2028-09 | 0 | 0 | 0
2028 | 10 | 2028-10 | 0 | 0 | 0
2028 | 11 | 2028-11 | 1 | 1396879.8 | 0
2028 | 12 | 2028-12 | 0 | 0 | 0
2029 | 1 | 2029-01 | 0 | 0 | 0
2029 | 2 | 2029-02 | 0 | 0 | 0
2029 | 3 | 2029-03 | 0 | 0 | 0
2029 | 4 | 2029-04 | 0 | 0 | 0
2029 | 5 | 2029-05 | 0 | 0 | 0
2029 | 6 | 2029-06 | 0 | 0 | 0
2029 | 7 | 2029-07 | 0 | 0 | 0
2029 | 8 | 2029-08 | 1 | 48137.6663 | 0
2029 | 9 | 2029-09 | 0 | 0 | 0
2029 | 10 | 2029-10 | 1 | 448044.37 | 0
2029 | 11 | 2029-11 | 0 | 0 | 0
2029 | 12 | 2029-12 | 1 | 1734957.675 | 0
2030 | 1 | 2030-01 | 0 | 0 | 0
2030 | 2 | 2030-02 | 0 | 0 | 0
2030 | 3 | 2030-03 | 0 | 0 | 0
2030 | 4 | 2030-04 | 0 | 0 | 0
2030 | 5 | 2030-05 | 0 | 0 | 0
2030 | 6 | 2030-06 | 0 | 0 | 0
2030 | 7 | 2030-07 | 0 | 0 | 0
2030 | 8 | 2030-08 | 0 | 0 | 0
2030 | 9 | 2030-09 | 0 | 0 | 0
2030 | 10 | 2030-10 | 1 | 333898.7334 | 0
2030 | 11 | 2030-11 | 1 | 15402.11 | 0
2030 | 12 | 2030-12 | 3 | 2102727.5415 | 0
2031 | 1 | 2031-01 | 1 | 8690.9 | 0
2031 | 2 | 2031-02 | 1 | 13253.62 | 0
2031 | 3 | 2031-03 | 0 | 0 | 0
2031 | 4 | 2031-04 | 0 | 0 | 0
2031 | 5 | 2031-05 | 0 | 0 | 0
2031 | 6 | 2031-06 | 0 | 0 | 0
2031 | 7 | 2031-07 | 0 | 0 | 0
2031 | 8 | 2031-08 | 0 | 0 | 0
2031 | 9 | 2031-09 | 0 | 0 | 0
2031 | 10 | 2031-10 | 0 | 0 | 0
2031 | 11 | 2031-11 | 0 | 0 | 0
2031 | 12 | 2031-12 | 1 | 293752.19 | 0
2032 | 1 | 2032-01 | 0 | 0 | 0
2032 | 2 | 2032-02 | 0 | 0 | 0
2032 | 3 | 2032-03 | 1 | 53621.44 | 0
2032 | 4 | 2032-04 | 0 | 0 | 0
2032 | 5 | 2032-05 | 0 | 0 | 0
2032 | 6 | 2032-06 | 1 | 1671724.9125 | 0
2032 | 7 | 2032-07 | 1 | 837193.7 | 0
2032 | 8 | 2032-08 | 0 | 0 | 0
2032 | 9 | 2032-09 | 1 | 43496.537 | 0
2032 | 10 | 2032-10 | 0 | 0 | 0
2032 | 11 | 2032-11 | 1 | 412750.4 | 0
2032 | 12 | 2032-12 | 1 | 79350 | 1
2033 | 1 | 2033-01 | 0 | 0 | 0
2033 | 2 | 2033-02 | 1 | 167051.5 | 0
2033 | 3 | 2033-03 | 0 | 0 | 0
2033 | 4 | 2033-04 | 0 | 0 | 0
2033 | 5 | 2033-05 | 1 | 2331334.4 | 0
2033 | 6 | 2033-06 | 0 | 0 | 0
2033 | 7 | 2033-07 | 0 | 0 | 0
2033 | 8 | 2033-08 | 0 | 0 | 0
2033 | 9 | 2033-09 | 0 | 0 | 0
2033 | 10 | 2033-10 | 0 | 0 | 0
2033 | 11 | 2033-11 | 1 | 26123.4895 | 0
2033 | 12 | 2033-12 | 0 | 0 | 0
2034 | 1 | 2034-01 | 1 | 129716.6715 | 0
2034 | 2 | 2034-02 | 0 | 0 | 0
2034 | 3 | 2034-03 | 0 | 0 | 0
2034 | 4 | 2034-04 | 0 | 0 | 0
2034 | 5 | 2034-05 | 0 | 0 | 0
2034 | 6 | 2034-06 | 0 | 0 | 0
2034 | 7 | 2034-07 | 0 | 0 | 0
2034 | 8 | 2034-08 | 0 | 0 | 0
2034 | 9 | 2034-09 | 0 | 0 | 0
2034 | 10 | 2034-10 | 0 | 0 | 0
2034 | 11 | 2034-11 | 0 | 0 | 0
2034 | 12 | 2034-12 | 0 | 0 | 0
2035 | 1 | 2035-01 | 0 | 0 | 0
2035 | 2 | 2035-02 | 0 | 0 | 0
2035 | 3 | 2035-03 | 0 | 0 | 0
2035 | 4 | 2035-04 | 2 | 225311.14 | 1
2035 | 5 | 2035-05 | 0 | 0 | 0
2035 | 6 | 2035-06 | 0 | 0 | 0
2035 | 7 | 2035-07 | 1 | 1412174.0475 | 0
2035 | 8 | 2035-08 | 0 | 0 | 0
2035 | 9 | 2035-09 | 0 | 0 | 0
2035 | 10 | 2035-10 | 1 | 1799636.88 | 0
2035 | 11 | 2035-11 | 0 | 0 | 0
2035 | 12 | 2035-12 | 0 | 0 | 0
2036 | 1 | 2036-01 | 0 | 0 | 0
2036 | 2 | 2036-02 | 0 | 0 | 0
2036 | 3 | 2036-03 | 0 | 0 | 0
2036 | 4 | 2036-04 | 0 | 0 | 0
2036 | 5 | 2036-05 | 0 | 0 | 0
2036 | 6 | 2036-06 | 1 | 358316.0643 | 0
2036 | 7 | 2036-07 | 0 | 0 | 0
2036 | 8 | 2036-08 | 0 | 0 | 0
2036 | 9 | 2036-09 | 0 | 0 | 0
2036 | 10 | 2036-10 | 1 | 736091.4 | 0
2036 | 11 | 2036-11 | 1 | 82956.2132 | 0
2036 | 12 | 2036-12 | 2 | 402954.5399 | 0
2037 | 1 | 2037-01 | 0 | 0 | 0
2037 | 2 | 2037-02 | 0 | 0 | 0
2037 | 3 | 2037-03 | 0 | 0 | 0
2037 | 4 | 2037-04 | 0 | 0 | 0
2037 | 5 | 2037-05 | 0 | 0 | 0
2037 | 6 | 2037-06 | 0 | 0 | 0
2037 | 7 | 2037-07 | 1 | 229094.3179 | 0
2037 | 8 | 2037-08 | 1 | 838596 | 0
2037 | 9 | 2037-09 | 0 | 0 | 0
2037 | 10 | 2037-10 | 1 | 540906.7577 | 0
2037 | 11 | 2037-11 | 0 | 0 | 0
2037 | 12 | 2037-12 | 1 | 6137.975 | 0
2038 | 1 | 2038-01 | 1 | 33451.5635 | 0
2038 | 2 | 2038-02 | 0 | 0 | 0
2038 | 3 | 2038-03 | 0 | 0 | 0
2038 | 4 | 2038-04 | 1 | 311398.7981 | 0
2038 | 5 | 2038-05 | 1 | 185150 | 1
2038 | 6 | 2038-06 | 0 | 0 | 0
2038 | 7 | 2038-07 | 0 | 0 | 0
2038 | 8 | 2038-08 | 0 | 0 | 0
2038 | 9 | 2038-09 | 1 | 252737 | 0
2038 | 10 | 2038-10 | 2 | 2021842.1425 | 0
2038 | 11 | 2038-11 | 0 | 0 | 0
2038 | 12 | 2038-12 | 1 | 12166.8 | 1
2039 | 1 | 2039-01 | 0 | 0 | 0
2039 | 2 | 2039-02 | 0 | 0 | 0
2039 | 3 | 2039-03 | 0 | 0 | 0
2039 | 4 | 2039-04 | 0 | 0 | 0
2039 | 5 | 2039-05 | 0 | 0 | 0
2039 | 6 | 2039-06 | 0 | 0 | 0
2039 | 7 | 2039-07 | 0 | 0 | 0
2039 | 8 | 2039-08 | 0 | 0 | 0
2039 | 9 | 2039-09 | 0 | 0 | 0
2039 | 10 | 2039-10 | 1 | 1619959.2637 | 0
2039 | 11 | 2039-11 | 0 | 0 | 0
2039 | 12 | 2039-12 | 1 | 48034.2 | 0
2040 | 1 | 2040-01 | 0 | 0 | 0
2040 | 2 | 2040-02 | 1 | 26560.8063 | 1
2040 | 3 | 2040-03 | 1 | 237403.9 | 0
2040 | 4 | 2040-04 | 0 | 0 | 0
2040 | 5 | 2040-05 | 0 | 0 | 0
2040 | 6 | 2040-06 | 0 | 0 | 0
2040 | 7 | 2040-07 | 0 | 0 | 0
2040 | 8 | 2040-08 | 1 | 1981177.1 | 0
2040 | 9 | 2040-09 | 0 | 0 | 0
2040 | 10 | 2040-10 | 0 | 0 | 0
2040 | 11 | 2040-11 | 0 | 0 | 0
2040 | 12 | 2040-12 | 0 | 0 | 0
2041 | 1 | 2041-01 | 0 | 0 | 0
2041 | 2 | 2041-02 | 2 | 193487.3758 | 2
2041 | 3 | 2041-03 | 0 | 0 | 0
2041 | 4 | 2041-04 | 0 | 0 | 0
2041 | 5 | 2041-05 | 1 | 14380.36 | 0
2041 | 6 | 2041-06 | 0 | 0 | 0
2041 | 7 | 2041-07 | 0 | 0 | 0
2041 | 8 | 2041-08 | 1 | 759988.1063 | 0
2041 | 9 | 2041-09 | 0 | 0 | 0
2041 | 10 | 2041-10 | 0 | 0 | 0
2041 | 11 | 2041-11 | 0 | 0 | 0
2041 | 12 | 2041-12 | 1 | 228918.85 | 0
2042 | 1 | 2042-01 | 0 | 0 | 0
2042 | 2 | 2042-02 | 1 | 175382.4 | 0
2042 | 3 | 2042-03 | 1 | 28412.7881 | 0
2042 | 4 | 2042-04 | 0 | 0 | 0
2042 | 5 | 2042-05 | 2 | 1244847.0075 | 0
2042 | 6 | 2042-06 | 1 | 39297.2201 | 0
2042 | 7 | 2042-07 | 2 | 436917.2229 | 0
2042 | 8 | 2042-08 | 2 | 147300 | 1
2042 | 9 | 2042-09 | 0 | 0 | 0
2042 | 10 | 2042-10 | 0 | 0 | 0
2042 | 11 | 2042-11 | 0 | 0 | 0
2042 | 12 | 2042-12 | 1 | 241467.9056 | 0
2043 | 1 | 2043-01 | 0 | 0 | 0
2043 | 2 | 2043-02 | 0 | 0 | 0
2043 | 3 | 2043-03 | 1 | 413800.2 | 0
2043 | 4 | 2043-04 | 0 | 0 | 0
2043 | 5 | 2043-05 | 0 | 0 | 0
2043 | 6 | 2043-06 | 0 | 0 | 0
2043 | 7 | 2043-07 | 0 | 0 | 0
2043 | 8 | 2043-08 | 0 | 0 | 0
2043 | 9 | 2043-09 | 0 | 0 | 0
2043 | 10 | 2043-10 | 0 | 0 | 0
2043 | 11 | 2043-11 | 2 | 916841.42 | 1
2043 | 12 | 2043-12 | 0 | 0 | 0
2044 | 1 | 2044-01 | 0 | 0 | 0
2044 | 2 | 2044-02 | 0 | 0 | 0
2044 | 3 | 2044-03 | 1 | 62094.12 | 0
2044 | 4 | 2044-04 | 0 | 0 | 0
2044 | 5 | 2044-05 | 0 | 0 | 0
2044 | 6 | 2044-06 | 0 | 0 | 0
2044 | 7 | 2044-07 | 3 | 781479.6216 | 1
2044 | 8 | 2044-08 | 1 | 103387.5886 | 0
2044 | 9 | 2044-09 | 0 | 0 | 0
2044 | 10 | 2044-10 | 1 | 1938960.808 | 0
2044 | 11 | 2044-11 | 0 | 0 | 0
2044 | 12 | 2044-12 | 1 | 71935.517 | 0
2045 | 1 | 2045-01 | 0 | 0 | 0
2045 | 2 | 2045-02 | 0 | 0 | 0
2045 | 3 | 2045-03 | 0 | 0 | 0
2045 | 4 | 2045-04 | 0 | 0 | 0
2045 | 5 | 2045-05 | 1 | 23087.7635 | 0
2045 | 6 | 2045-06 | 0 | 0 | 0
2045 | 7 | 2045-07 | 1 | 1257984.63 | 0
2045 | 8 | 2045-08 | 0 | 0 | 0
2045 | 9 | 2045-09 | 1 | 6776.8 | 0
2045 | 10 | 2045-10 | 0 | 0 | 0
2045 | 11 | 2045-11 | 1 | 410659.34 | 0
2045 | 12 | 2045-12 | 0 | 0 | 0
2046 | 1 | 2046-01 | 0 | 0 | 0
2046 | 2 | 2046-02 | 0 | 0 | 0
2046 | 3 | 2046-03 | 0 | 0 | 0
2046 | 4 | 2046-04 | 0 | 0 | 0
2046 | 5 | 2046-05 | 1 | 589599.1625 | 0
2046 | 6 | 2046-06 | 0 | 0 | 0
2046 | 7 | 2046-07 | 0 | 0 | 0
2046 | 8 | 2046-08 | 0 | 0 | 0
2046 | 9 | 2046-09 | 0 | 0 | 0
2046 | 10 | 2046-10 | 0 | 0 | 0
2046 | 11 | 2046-11 | 0 | 0 | 0
2046 | 12 | 2046-12 | 1 | 331155.7375 | 0
2047 | 1 | 2047-01 | 0 | 0 | 0
2047 | 2 | 2047-02 | 0 | 0 | 0
2047 | 3 | 2047-03 | 1 | 183773.699 | 0
2047 | 4 | 2047-04 | 1 | 1364168.78 | 0
2047 | 5 | 2047-05 | 0 | 0 | 0
2047 | 6 | 2047-06 | 0 | 0 | 0
2047 | 7 | 2047-07 | 0 | 0 | 0
2047 | 8 | 2047-08 | 0 | 0 | 0
2047 | 9 | 2047-09 | 1 | 100666.7 | 0
2047 | 10 | 2047-10 | 0 | 0 | 0
2047 | 11 | 2047-11 | 0 | 0 | 0
2047 | 12 | 2047-12 | 1 | 229990.7 | 0
2048 | 1 | 2048-01 | 3 | 1264083.136 | 0
2048 | 2 | 2048-02 | 1 | 96216.36 | 0
2048 | 3 | 2048-03 | 1 | 28031.7 | 0
2048 | 4 | 2048-04 | 0 | 0 | 0
2048 | 5 | 2048-05 | 0 | 0 | 0
2048 | 6 | 2048-06 | 0 | 0 | 0
2048 | 7 | 2048-07 | 0 | 0 | 0
2048 | 8 | 2048-08 | 0 | 0 | 0
2048 | 9 | 2048-09 | 0 | 0 | 0
2048 | 10 | 2048-10 | 0 | 0 | 0
2048 | 11 | 2048-11 | 1 | 29979.5 | 1
2048 | 12 | 2048-12 | 1 | 1637906.296 | 0
2049 | 1 | 2049-01 | 0 | 0 | 0
2049 | 2 | 2049-02 | 0 | 0 | 0
2049 | 3 | 2049-03 | 1 | 537306.864 | 0
2049 | 4 | 2049-04 | 1 | 316840.8906 | 0
2049 | 5 | 2049-05 | 0 | 0 | 0
2049 | 6 | 2049-06 | 0 | 0 | 0
2049 | 7 | 2049-07 | 0 | 0 | 0
2049 | 8 | 2049-08 | 0 | 0 | 0
2049 | 9 | 2049-09 | 1 | 166570.6543 | 0
2049 | 10 | 2049-10 | 0 | 0 | 0
2049 | 11 | 2049-11 | 0 | 0 | 0
2049 | 12 | 2049-12 | 0 | 0 | 0
2050 | 1 | 2050-01 | 0 | 0 | 0
2050 | 2 | 2050-02 | 0 | 0 | 0
2050 | 3 | 2050-03 | 0 | 0 | 0
2050 | 4 | 2050-04 | 1 | 394782.2 | 0
2050 | 5 | 2050-05 | 0 | 0 | 0
2050 | 6 | 2050-06 | 1 | 573049.868 | 0
2050 | 7 | 2050-07 | 1 | 243402.9467 | 0
2050 | 8 | 2050-08 | 0 | 0 | 0
2050 | 9 | 2050-09 | 1 | 169732.8639 | 0
2050 | 10 | 2050-10 | 0 | 0 | 0
2050 | 11 | 2050-11 | 0 | 0 | 0
2050 | 12 | 2050-12 | 1 | 92033.116 | 0

## stats_annees
year | renovations_started | renovations_instant | budget_acompte | budget_solde | budget_instant | budget_total_paye | gain_year | gain_cumulatif | gain (%) | Renov moyennes
2026 | 6 | 1 | 507937.1211 | 1035007.8445 | 445300 | 1988244.9657 | 338.2705 | 338.2705 | 21.2983 | 4.36
2027 | 6 | 0 | 531905.1224 | 1418652.48 | 0 | 1950557.6024 | 288.506 | 626.7765 | 22.4057 | 4.36
2028 | 1 | 0 | 279375.96 | 1705708.6496 | 0 | 1985084.6096 | 542.9081 | 1169.6846 | 24.4894 | 4.36
2029 | 3 | 0 | 446227.9423 | 1514449.4691 | 0 | 1960677.4113 | 241.1522 | 1410.8368 | 25.415 | 4.36
2030 | 5 | 0 | 490405.677 | 1442385.5452 | 0 | 1932791.2222 | 367.754 | 1778.5908 | 26.8265 | 4.36
2031 | 3 | 0 | 63139.342 | 1924758.9187 | 0 | 1987898.2607 | 528.8185 | 2307.4094 | 28.8561 | 4.36
2032 | 6 | 1 | 603757.3979 | 1312651.4136 | 79350 | 1995758.8115 | 324.5312 | 2631.9406 | 30.1017 | 4.36
2033 | 3 | 0 | 504901.8779 | 1491919.9216 | 0 | 1996821.7995 | 324.0036 | 2955.9442 | 31.3453 | 4.36
2034 | 1 | 0 | 25943.3343 | 1968840.8572 | 0 | 1994784.1915 | 427.9298 | 3383.874 | 32.9878 | 4.36
2035 | 4 | 1 | 684774.4135 | 1299388.15 | 13250 | 1997412.5635 | 113.5098 | 3497.3837 | 33.4234 | 4.36
2036 | 5 | 0 | 316063.6435 | 1675129.5145 | 0 | 1991193.158 | 421.6903 | 3919.074 | 35.0419 | 4.36
2037 | 4 | 0 | 322947.0101 | 1649745.8039 | 0 | 1972692.814 | 323.981 | 4243.055 | 36.2854 | 4.36
2038 | 7 | 2 | 523885.9008 | 1148946.6893 | 197316.8 | 1870149.3901 | 372.5088 | 4615.5639 | 37.7151 | 4.36
2039 | 2 | 0 | 333598.6927 | 1617473.714 | 0 | 1951072.4068 | 265.5301 | 4881.094 | 38.7343 | 4.36
2040 | 3 | 1 | 443716.2 | 1524317.891 | 26560.8063 | 1994594.8973 | 209.0189 | 5090.1128 | 39.5365 | 4.36
2041 | 5 | 2 | 200657.4633 | 1584941.68 | 193487.3758 | 1979086.519 | 708.1353 | 5798.2481 | 42.2544 | 4.36
2042 | 10 | 1 | 453787.705 | 1443334.8884 | 44686.0192 | 1941808.6127 | 447.3099 | 6245.5581 | 43.9713 | 4.36
2043 | 3 | 1 | 211678.3 | 1505485.9445 | 272250.12 | 1989414.3645 | 839.4782 | 7085.0362 | 47.1933 | 4.36
2044 | 7 | 1 | 561761.531 | 1154002.1041 | 149050 | 1864813.6352 | 114.2774 | 7199.3137 | 47.6319 | 4.36
2045 | 4 | 0 | 339701.7067 | 1632608.7108 | 0 | 1972310.4175 | 372.7185 | 7572.0322 | 49.0625 | 4.36
2046 | 2 | 0 | 184150.98 | 1806594.506 | 0 | 1990745.486 | 416.8799 | 7988.9121 | 50.6625 | 4.36
2047 | 4 | 0 | 375719.9758 | 1583811.9332 | 0 | 1959531.909 | 237.4284 | 8226.3405 | 51.5738 | 4.36
2048 | 7 | 1 | 605247.4984 | 1294657.5168 | 29979.5 | 1929884.5152 | 207.0683 | 8433.4088 | 52.3685 | 4.36
2049 | 3 | 0 | 204143.6818 | 1697054.2727 | 0 | 1901197.9545 | 359.2695 | 8792.6783 | 53.7475 | 4.36
2050 | 5 | 0 | 294600.1989 | 1608246.2869 | 0 | 1902846.4858 | 628.3843 | 9421.0625 | 56.1593 | 4.36

## disponibilite_detail
period | year | month | category | nb_buildings_total | nb_buildings_active | limit_20pct | taux_occupation | respect_limit | is_exempt
2026-01 | 2026 | 1 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2026-01 | 2026 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2026-01 | 2026 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2026-02 | 2026 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2026-02 | 2026 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-02 | 2026 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2026-03 | 2026 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2026-03 | 2026 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-03 | 2026 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2026-04 | 2026 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2026-04 | 2026 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-04 | 2026 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2026-05 | 2026 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2026-05 | 2026 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-05 | 2026 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2026-06 | 2026 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2026-06 | 2026 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2026-06 | 2026 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2026-07 | 2026 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2026-07 | 2026 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2026-07 | 2026 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2026-08 | 2026 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2026-08 | 2026 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2026-08 | 2026 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2026-09 | 2026 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2026-09 | 2026 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-09 | 2026 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2026-10 | 2026 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2026-10 | 2026 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-10 | 2026 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2026-11 | 2026 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2026-11 | 2026 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-11 | 2026 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2026-12 | 2026 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2026-12 | 2026 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2026-12 | 2026 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2027-01 | 2027 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2027-01 | 2027 | 1 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2027-01 | 2027 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2027-02 | 2027 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2027-02 | 2027 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2027-02 | 2027 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2027-03 | 2027 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2027-03 | 2027 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2027-03 | 2027 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2027-04 | 2027 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2027-04 | 2027 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2027-04 | 2027 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2027-05 | 2027 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2027-05 | 2027 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2027-05 | 2027 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2027-06 | 2027 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2027-06 | 2027 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2027-06 | 2027 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2027-07 | 2027 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2027-07 | 2027 | 7 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2027-07 | 2027 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2027-08 | 2027 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2027-08 | 2027 | 8 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2027-08 | 2027 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2027-09 | 2027 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2027-09 | 2027 | 9 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2027-09 | 2027 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2027-10 | 2027 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2027-10 | 2027 | 10 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2027-10 | 2027 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2027-11 | 2027 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2027-11 | 2027 | 11 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2027-11 | 2027 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2027-12 | 2027 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2027-12 | 2027 | 12 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2027-12 | 2027 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2028-01 | 2028 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2028-01 | 2028 | 1 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2028-01 | 2028 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2028-02 | 2028 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2028-02 | 2028 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2028-02 | 2028 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2028-03 | 2028 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2028-03 | 2028 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-03 | 2028 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2028-04 | 2028 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2028-04 | 2028 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-04 | 2028 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2028-05 | 2028 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2028-05 | 2028 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-05 | 2028 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2028-06 | 2028 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2028-06 | 2028 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-06 | 2028 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2028-07 | 2028 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2028-07 | 2028 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2028-07 | 2028 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2028-08 | 2028 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2028-08 | 2028 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2028-08 | 2028 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2028-09 | 2028 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2028-09 | 2028 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-09 | 2028 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2028-10 | 2028 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2028-10 | 2028 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2028-10 | 2028 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2028-11 | 2028 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2028-11 | 2028 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2028-11 | 2028 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2028-12 | 2028 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2028-12 | 2028 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2028-12 | 2028 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2029-01 | 2029 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2029-01 | 2029 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2029-01 | 2029 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2029-02 | 2029 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2029-02 | 2029 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2029-02 | 2029 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2029-03 | 2029 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2029-03 | 2029 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2029-03 | 2029 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2029-04 | 2029 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2029-04 | 2029 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2029-04 | 2029 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2029-05 | 2029 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2029-05 | 2029 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2029-05 | 2029 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2029-06 | 2029 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2029-06 | 2029 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2029-06 | 2029 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2029-07 | 2029 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2029-07 | 2029 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2029-07 | 2029 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2029-08 | 2029 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2029-08 | 2029 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2029-08 | 2029 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2029-09 | 2029 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2029-09 | 2029 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2029-09 | 2029 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2029-10 | 2029 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2029-10 | 2029 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2029-10 | 2029 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2029-11 | 2029 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2029-11 | 2029 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2029-11 | 2029 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2029-12 | 2029 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2029-12 | 2029 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2029-12 | 2029 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2030-01 | 2030 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2030-01 | 2030 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2030-01 | 2030 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2030-02 | 2030 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2030-02 | 2030 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-02 | 2030 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2030-03 | 2030 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2030-03 | 2030 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-03 | 2030 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2030-04 | 2030 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2030-04 | 2030 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-04 | 2030 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2030-05 | 2030 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2030-05 | 2030 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-05 | 2030 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2030-06 | 2030 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2030-06 | 2030 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-06 | 2030 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2030-07 | 2030 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2030-07 | 2030 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2030-07 | 2030 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2030-08 | 2030 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2030-08 | 2030 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2030-08 | 2030 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2030-09 | 2030 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2030-09 | 2030 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-09 | 2030 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2030-10 | 2030 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2030-10 | 2030 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-10 | 2030 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2030-11 | 2030 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2030-11 | 2030 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-11 | 2030 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2030-12 | 2030 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2030-12 | 2030 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2030-12 | 2030 | 12 | Administration | 5 | 1 | 1 | 0.2 | ✓
2031-01 | 2031 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2031-01 | 2031 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2031-01 | 2031 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2031-02 | 2031 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2031-02 | 2031 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-02 | 2031 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2031-03 | 2031 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2031-03 | 2031 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-03 | 2031 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2031-04 | 2031 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2031-04 | 2031 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-04 | 2031 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2031-05 | 2031 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2031-05 | 2031 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-05 | 2031 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2031-06 | 2031 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2031-06 | 2031 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-06 | 2031 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2031-07 | 2031 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2031-07 | 2031 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2031-07 | 2031 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2031-08 | 2031 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2031-08 | 2031 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2031-08 | 2031 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2031-09 | 2031 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2031-09 | 2031 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-09 | 2031 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2031-10 | 2031 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2031-10 | 2031 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-10 | 2031 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2031-11 | 2031 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2031-11 | 2031 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-11 | 2031 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2031-12 | 2031 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2031-12 | 2031 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2031-12 | 2031 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2032-01 | 2032 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2032-01 | 2032 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2032-01 | 2032 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2032-02 | 2032 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2032-02 | 2032 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2032-02 | 2032 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2032-03 | 2032 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2032-03 | 2032 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-03 | 2032 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2032-04 | 2032 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2032-04 | 2032 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-04 | 2032 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2032-05 | 2032 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2032-05 | 2032 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2032-05 | 2032 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2032-06 | 2032 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2032-06 | 2032 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-06 | 2032 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2032-07 | 2032 | 7 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2032-07 | 2032 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2032-07 | 2032 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2032-08 | 2032 | 8 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2032-08 | 2032 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2032-08 | 2032 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2032-09 | 2032 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2032-09 | 2032 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-09 | 2032 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2032-10 | 2032 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2032-10 | 2032 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-10 | 2032 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2032-11 | 2032 | 11 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2032-11 | 2032 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2032-11 | 2032 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2032-12 | 2032 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2032-12 | 2032 | 12 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2032-12 | 2032 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2033-01 | 2033 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2033-01 | 2033 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2033-01 | 2033 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2033-02 | 2033 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2033-02 | 2033 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-02 | 2033 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2033-03 | 2033 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2033-03 | 2033 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-03 | 2033 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2033-04 | 2033 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2033-04 | 2033 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-04 | 2033 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2033-05 | 2033 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2033-05 | 2033 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-05 | 2033 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2033-06 | 2033 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2033-06 | 2033 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-06 | 2033 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2033-07 | 2033 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2033-07 | 2033 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2033-07 | 2033 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2033-08 | 2033 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2033-08 | 2033 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2033-08 | 2033 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2033-09 | 2033 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2033-09 | 2033 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-09 | 2033 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2033-10 | 2033 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2033-10 | 2033 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-10 | 2033 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2033-11 | 2033 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2033-11 | 2033 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-11 | 2033 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2033-12 | 2033 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2033-12 | 2033 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2033-12 | 2033 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2034-01 | 2034 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2034-01 | 2034 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2034-01 | 2034 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2034-02 | 2034 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2034-02 | 2034 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2034-02 | 2034 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2034-03 | 2034 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2034-03 | 2034 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2034-03 | 2034 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2034-04 | 2034 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2034-04 | 2034 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-04 | 2034 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2034-05 | 2034 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2034-05 | 2034 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-05 | 2034 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2034-06 | 2034 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2034-06 | 2034 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-06 | 2034 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2034-07 | 2034 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2034-07 | 2034 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2034-07 | 2034 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2034-08 | 2034 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2034-08 | 2034 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2034-08 | 2034 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2034-09 | 2034 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2034-09 | 2034 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-09 | 2034 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2034-10 | 2034 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2034-10 | 2034 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-10 | 2034 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2034-11 | 2034 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2034-11 | 2034 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-11 | 2034 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2034-12 | 2034 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2034-12 | 2034 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2034-12 | 2034 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2035-01 | 2035 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2035-01 | 2035 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2035-01 | 2035 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2035-02 | 2035 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2035-02 | 2035 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2035-02 | 2035 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2035-03 | 2035 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2035-03 | 2035 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2035-03 | 2035 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2035-04 | 2035 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2035-04 | 2035 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2035-04 | 2035 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2035-05 | 2035 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2035-05 | 2035 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2035-05 | 2035 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2035-06 | 2035 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2035-06 | 2035 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2035-06 | 2035 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2035-07 | 2035 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2035-07 | 2035 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2035-07 | 2035 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2035-08 | 2035 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2035-08 | 2035 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2035-08 | 2035 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2035-09 | 2035 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2035-09 | 2035 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2035-09 | 2035 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2035-10 | 2035 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2035-10 | 2035 | 10 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2035-10 | 2035 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2035-11 | 2035 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2035-11 | 2035 | 11 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2035-11 | 2035 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2035-12 | 2035 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2035-12 | 2035 | 12 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2035-12 | 2035 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2036-01 | 2036 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2036-01 | 2036 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2036-01 | 2036 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2036-02 | 2036 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2036-02 | 2036 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-02 | 2036 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2036-03 | 2036 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2036-03 | 2036 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-03 | 2036 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2036-04 | 2036 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2036-04 | 2036 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-04 | 2036 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2036-05 | 2036 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2036-05 | 2036 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-05 | 2036 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2036-06 | 2036 | 6 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-06 | 2036 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-06 | 2036 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2036-07 | 2036 | 7 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-07 | 2036 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2036-07 | 2036 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2036-08 | 2036 | 8 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-08 | 2036 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2036-08 | 2036 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2036-09 | 2036 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-09 | 2036 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-09 | 2036 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2036-10 | 2036 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-10 | 2036 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-10 | 2036 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2036-11 | 2036 | 11 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2036-11 | 2036 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-11 | 2036 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2036-12 | 2036 | 12 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2036-12 | 2036 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2036-12 | 2036 | 12 | Administration | 5 | 1 | 1 | 0.2 | ✓
2037-01 | 2037 | 1 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2037-01 | 2037 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2037-01 | 2037 | 1 | Administration | 5 | 1 | 1 | 0.2 | ✓
2037-02 | 2037 | 2 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2037-02 | 2037 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-02 | 2037 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2037-03 | 2037 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2037-03 | 2037 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-03 | 2037 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2037-04 | 2037 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2037-04 | 2037 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2037-04 | 2037 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2037-05 | 2037 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2037-05 | 2037 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2037-05 | 2037 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2037-06 | 2037 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2037-06 | 2037 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2037-06 | 2037 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2037-07 | 2037 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2037-07 | 2037 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2037-07 | 2037 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2037-08 | 2037 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2037-08 | 2037 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2037-08 | 2037 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2037-09 | 2037 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2037-09 | 2037 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-09 | 2037 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2037-10 | 2037 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2037-10 | 2037 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-10 | 2037 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2037-11 | 2037 | 11 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2037-11 | 2037 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-11 | 2037 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2037-12 | 2037 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2037-12 | 2037 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2037-12 | 2037 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2038-01 | 2038 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2038-01 | 2038 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2038-01 | 2038 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2038-02 | 2038 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2038-02 | 2038 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2038-02 | 2038 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2038-03 | 2038 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2038-03 | 2038 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2038-03 | 2038 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2038-04 | 2038 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2038-04 | 2038 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2038-04 | 2038 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2038-05 | 2038 | 5 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2038-05 | 2038 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2038-05 | 2038 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2038-06 | 2038 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2038-06 | 2038 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2038-06 | 2038 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2038-07 | 2038 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2038-07 | 2038 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2038-07 | 2038 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2038-08 | 2038 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2038-08 | 2038 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2038-08 | 2038 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2038-09 | 2038 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2038-09 | 2038 | 9 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2038-09 | 2038 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2038-10 | 2038 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2038-10 | 2038 | 10 | Enseignement | 26 | 4 | 5.2 | 0.15385 | ✓
2038-10 | 2038 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2038-11 | 2038 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2038-11 | 2038 | 11 | Enseignement | 26 | 4 | 5.2 | 0.15385 | ✓
2038-11 | 2038 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2038-12 | 2038 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2038-12 | 2038 | 12 | Enseignement | 26 | 3 | 5.2 | 0.11538 | ✓
2038-12 | 2038 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2039-01 | 2039 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2039-01 | 2039 | 1 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2039-01 | 2039 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2039-02 | 2039 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2039-02 | 2039 | 2 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2039-02 | 2039 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2039-03 | 2039 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2039-03 | 2039 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-03 | 2039 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2039-04 | 2039 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2039-04 | 2039 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-04 | 2039 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2039-05 | 2039 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2039-05 | 2039 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-05 | 2039 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2039-06 | 2039 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2039-06 | 2039 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-06 | 2039 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2039-07 | 2039 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2039-07 | 2039 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2039-07 | 2039 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2039-08 | 2039 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2039-08 | 2039 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2039-08 | 2039 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2039-09 | 2039 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2039-09 | 2039 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2039-09 | 2039 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2039-10 | 2039 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2039-10 | 2039 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-10 | 2039 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2039-11 | 2039 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2039-11 | 2039 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-11 | 2039 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2039-12 | 2039 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2039-12 | 2039 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2039-12 | 2039 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2040-01 | 2040 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2040-01 | 2040 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2040-01 | 2040 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2040-02 | 2040 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2040-02 | 2040 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2040-02 | 2040 | 2 | Administration | 5 | 1 | 1 | 0.2 | ✓
2040-03 | 2040 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2040-03 | 2040 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2040-03 | 2040 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2040-04 | 2040 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2040-04 | 2040 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2040-04 | 2040 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2040-05 | 2040 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2040-05 | 2040 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-05 | 2040 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2040-06 | 2040 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2040-06 | 2040 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-06 | 2040 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2040-07 | 2040 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2040-07 | 2040 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2040-07 | 2040 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2040-08 | 2040 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2040-08 | 2040 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2040-08 | 2040 | 8 | Administration | 5 | 1 | 1 | 0.2 | ✓
2040-09 | 2040 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2040-09 | 2040 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-09 | 2040 | 9 | Administration | 5 | 1 | 1 | 0.2 | ✓
2040-10 | 2040 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2040-10 | 2040 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-10 | 2040 | 10 | Administration | 5 | 1 | 1 | 0.2 | ✓
2040-11 | 2040 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2040-11 | 2040 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-11 | 2040 | 11 | Administration | 5 | 1 | 1 | 0.2 | ✓
2040-12 | 2040 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2040-12 | 2040 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2040-12 | 2040 | 12 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-01 | 2041 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2041-01 | 2041 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2041-01 | 2041 | 1 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-02 | 2041 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2041-02 | 2041 | 2 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2041-02 | 2041 | 2 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-03 | 2041 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2041-03 | 2041 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2041-03 | 2041 | 3 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-04 | 2041 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2041-04 | 2041 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2041-04 | 2041 | 4 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-05 | 2041 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2041-05 | 2041 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2041-05 | 2041 | 5 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-06 | 2041 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2041-06 | 2041 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2041-06 | 2041 | 6 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-07 | 2041 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2041-07 | 2041 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2041-07 | 2041 | 7 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-08 | 2041 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2041-08 | 2041 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2041-08 | 2041 | 8 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-09 | 2041 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2041-09 | 2041 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2041-09 | 2041 | 9 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-10 | 2041 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2041-10 | 2041 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2041-10 | 2041 | 10 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-11 | 2041 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2041-11 | 2041 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2041-11 | 2041 | 11 | Administration | 5 | 1 | 1 | 0.2 | ✓
2041-12 | 2041 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2041-12 | 2041 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2041-12 | 2041 | 12 | Administration | 5 | 1 | 1 | 0.2 | ✓
2042-01 | 2042 | 1 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2042-01 | 2042 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2042-01 | 2042 | 1 | Administration | 5 | 1 | 1 | 0.2 | ✓
2042-02 | 2042 | 2 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2042-02 | 2042 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-02 | 2042 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2042-03 | 2042 | 3 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2042-03 | 2042 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-03 | 2042 | 3 | Administration | 5 | 1 | 1 | 0.2 | ✓
2042-04 | 2042 | 4 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2042-04 | 2042 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-04 | 2042 | 4 | Administration | 5 | 1 | 1 | 0.2 | ✓
2042-05 | 2042 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2042-05 | 2042 | 5 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2042-05 | 2042 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2042-06 | 2042 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2042-06 | 2042 | 6 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2042-06 | 2042 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2042-07 | 2042 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2042-07 | 2042 | 7 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2042-07 | 2042 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2042-08 | 2042 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2042-08 | 2042 | 8 | Enseignement | 26 | 3 | 5.2 | 0.11538 | ✓ | Exempté
2042-08 | 2042 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2042-09 | 2042 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2042-09 | 2042 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-09 | 2042 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2042-10 | 2042 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2042-10 | 2042 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-10 | 2042 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2042-11 | 2042 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2042-11 | 2042 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2042-11 | 2042 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2042-12 | 2042 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2042-12 | 2042 | 12 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2042-12 | 2042 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2043-01 | 2043 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2043-01 | 2043 | 1 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2043-01 | 2043 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2043-02 | 2043 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2043-02 | 2043 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-02 | 2043 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2043-03 | 2043 | 3 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-03 | 2043 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-03 | 2043 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2043-04 | 2043 | 4 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-04 | 2043 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-04 | 2043 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2043-05 | 2043 | 5 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-05 | 2043 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-05 | 2043 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2043-06 | 2043 | 6 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-06 | 2043 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-06 | 2043 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2043-07 | 2043 | 7 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-07 | 2043 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2043-07 | 2043 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2043-08 | 2043 | 8 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-08 | 2043 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2043-08 | 2043 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2043-09 | 2043 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-09 | 2043 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-09 | 2043 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2043-10 | 2043 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-10 | 2043 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-10 | 2043 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2043-11 | 2043 | 11 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2043-11 | 2043 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-11 | 2043 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2043-12 | 2043 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2043-12 | 2043 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2043-12 | 2043 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2044-01 | 2044 | 1 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2044-01 | 2044 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2044-01 | 2044 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2044-02 | 2044 | 2 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2044-02 | 2044 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2044-02 | 2044 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2044-03 | 2044 | 3 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2044-03 | 2044 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2044-03 | 2044 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2044-04 | 2044 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2044-04 | 2044 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2044-04 | 2044 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2044-05 | 2044 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2044-05 | 2044 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2044-05 | 2044 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2044-06 | 2044 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2044-06 | 2044 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2044-06 | 2044 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2044-07 | 2044 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2044-07 | 2044 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2044-07 | 2044 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2044-08 | 2044 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2044-08 | 2044 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2044-08 | 2044 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2044-09 | 2044 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2044-09 | 2044 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2044-09 | 2044 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2044-10 | 2044 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2044-10 | 2044 | 10 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2044-10 | 2044 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2044-11 | 2044 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2044-11 | 2044 | 11 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2044-11 | 2044 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2044-12 | 2044 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2044-12 | 2044 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2044-12 | 2044 | 12 | Administration | 5 | 1 | 1 | 0.2 | ✓
2045-01 | 2045 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2045-01 | 2045 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2045-01 | 2045 | 1 | Administration | 5 | 1 | 1 | 0.2 | ✓
2045-02 | 2045 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2045-02 | 2045 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-02 | 2045 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2045-03 | 2045 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2045-03 | 2045 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-03 | 2045 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2045-04 | 2045 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2045-04 | 2045 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-04 | 2045 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2045-05 | 2045 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2045-05 | 2045 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-05 | 2045 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2045-06 | 2045 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2045-06 | 2045 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-06 | 2045 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2045-07 | 2045 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2045-07 | 2045 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2045-07 | 2045 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2045-08 | 2045 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2045-08 | 2045 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2045-08 | 2045 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2045-09 | 2045 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2045-09 | 2045 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-09 | 2045 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2045-10 | 2045 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2045-10 | 2045 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-10 | 2045 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2045-11 | 2045 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2045-11 | 2045 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-11 | 2045 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2045-12 | 2045 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2045-12 | 2045 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2045-12 | 2045 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2046-01 | 2046 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2046-01 | 2046 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2046-01 | 2046 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2046-02 | 2046 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2046-02 | 2046 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2046-02 | 2046 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2046-03 | 2046 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2046-03 | 2046 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2046-03 | 2046 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2046-04 | 2046 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2046-04 | 2046 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2046-04 | 2046 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2046-05 | 2046 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2046-05 | 2046 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-05 | 2046 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2046-06 | 2046 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2046-06 | 2046 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-06 | 2046 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2046-07 | 2046 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2046-07 | 2046 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2046-07 | 2046 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2046-08 | 2046 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2046-08 | 2046 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2046-08 | 2046 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2046-09 | 2046 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2046-09 | 2046 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-09 | 2046 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2046-10 | 2046 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2046-10 | 2046 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-10 | 2046 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2046-11 | 2046 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2046-11 | 2046 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-11 | 2046 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2046-12 | 2046 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2046-12 | 2046 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2046-12 | 2046 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2047-01 | 2047 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2047-01 | 2047 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2047-01 | 2047 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2047-02 | 2047 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2047-02 | 2047 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2047-02 | 2047 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2047-03 | 2047 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2047-03 | 2047 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2047-03 | 2047 | 3 | Administration | 5 | 1 | 1 | 0.2 | ✓
2047-04 | 2047 | 4 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-04 | 2047 | 4 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2047-04 | 2047 | 4 | Administration | 5 | 1 | 1 | 0.2 | ✓
2047-05 | 2047 | 5 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-05 | 2047 | 5 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2047-05 | 2047 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2047-06 | 2047 | 6 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-06 | 2047 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2047-06 | 2047 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2047-07 | 2047 | 7 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-07 | 2047 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2047-07 | 2047 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2047-08 | 2047 | 8 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-08 | 2047 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2047-08 | 2047 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2047-09 | 2047 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-09 | 2047 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2047-09 | 2047 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2047-10 | 2047 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2047-10 | 2047 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2047-10 | 2047 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2047-11 | 2047 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2047-11 | 2047 | 11 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2047-11 | 2047 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2047-12 | 2047 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2047-12 | 2047 | 12 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2047-12 | 2047 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2048-01 | 2048 | 1 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2048-01 | 2048 | 1 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2048-01 | 2048 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2048-02 | 2048 | 2 | Sports | 15 | 2 | 3 | 0.13333 | ✓
2048-02 | 2048 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2048-02 | 2048 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2048-03 | 2048 | 3 | Sports | 15 | 3 | 3 | 0.2 | ✓
2048-03 | 2048 | 3 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2048-03 | 2048 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2048-04 | 2048 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2048-04 | 2048 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2048-04 | 2048 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2048-05 | 2048 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2048-05 | 2048 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2048-05 | 2048 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2048-06 | 2048 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2048-06 | 2048 | 6 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2048-06 | 2048 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2048-07 | 2048 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2048-07 | 2048 | 7 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2048-07 | 2048 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2048-08 | 2048 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2048-08 | 2048 | 8 | Enseignement | 26 | 0 | 5.2 | 0 | ✓ | Exempté
2048-08 | 2048 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2048-09 | 2048 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2048-09 | 2048 | 9 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2048-09 | 2048 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2048-10 | 2048 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2048-10 | 2048 | 10 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2048-10 | 2048 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2048-11 | 2048 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2048-11 | 2048 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2048-11 | 2048 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2048-12 | 2048 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2048-12 | 2048 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2048-12 | 2048 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2049-01 | 2049 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2049-01 | 2049 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2049-01 | 2049 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2049-02 | 2049 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2049-02 | 2049 | 2 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2049-02 | 2049 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2049-03 | 2049 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2049-03 | 2049 | 3 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2049-03 | 2049 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2049-04 | 2049 | 4 | Sports | 15 | 0 | 3 | 0 | ✓
2049-04 | 2049 | 4 | Enseignement | 26 | 3 | 5.2 | 0.11538 | ✓
2049-04 | 2049 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2049-05 | 2049 | 5 | Sports | 15 | 0 | 3 | 0 | ✓
2049-05 | 2049 | 5 | Enseignement | 26 | 3 | 5.2 | 0.11538 | ✓
2049-05 | 2049 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2049-06 | 2049 | 6 | Sports | 15 | 0 | 3 | 0 | ✓
2049-06 | 2049 | 6 | Enseignement | 26 | 3 | 5.2 | 0.11538 | ✓
2049-06 | 2049 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2049-07 | 2049 | 7 | Sports | 15 | 0 | 3 | 0 | ✓
2049-07 | 2049 | 7 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2049-07 | 2049 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2049-08 | 2049 | 8 | Sports | 15 | 0 | 3 | 0 | ✓
2049-08 | 2049 | 8 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓ | Exempté
2049-08 | 2049 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2049-09 | 2049 | 9 | Sports | 15 | 0 | 3 | 0 | ✓
2049-09 | 2049 | 9 | Enseignement | 26 | 2 | 5.2 | 0.076923 | ✓
2049-09 | 2049 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2049-10 | 2049 | 10 | Sports | 15 | 0 | 3 | 0 | ✓
2049-10 | 2049 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2049-10 | 2049 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2049-11 | 2049 | 11 | Sports | 15 | 0 | 3 | 0 | ✓
2049-11 | 2049 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2049-11 | 2049 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2049-12 | 2049 | 12 | Sports | 15 | 0 | 3 | 0 | ✓
2049-12 | 2049 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2049-12 | 2049 | 12 | Administration | 5 | 0 | 1 | 0 | ✓
2050-01 | 2050 | 1 | Sports | 15 | 0 | 3 | 0 | ✓
2050-01 | 2050 | 1 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2050-01 | 2050 | 1 | Administration | 5 | 0 | 1 | 0 | ✓
2050-02 | 2050 | 2 | Sports | 15 | 0 | 3 | 0 | ✓
2050-02 | 2050 | 2 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2050-02 | 2050 | 2 | Administration | 5 | 0 | 1 | 0 | ✓
2050-03 | 2050 | 3 | Sports | 15 | 0 | 3 | 0 | ✓
2050-03 | 2050 | 3 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2050-03 | 2050 | 3 | Administration | 5 | 0 | 1 | 0 | ✓
2050-04 | 2050 | 4 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-04 | 2050 | 4 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2050-04 | 2050 | 4 | Administration | 5 | 0 | 1 | 0 | ✓
2050-05 | 2050 | 5 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-05 | 2050 | 5 | Enseignement | 26 | 0 | 5.2 | 0 | ✓
2050-05 | 2050 | 5 | Administration | 5 | 0 | 1 | 0 | ✓
2050-06 | 2050 | 6 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-06 | 2050 | 6 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2050-06 | 2050 | 6 | Administration | 5 | 0 | 1 | 0 | ✓
2050-07 | 2050 | 7 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-07 | 2050 | 7 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2050-07 | 2050 | 7 | Administration | 5 | 0 | 1 | 0 | ✓
2050-08 | 2050 | 8 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-08 | 2050 | 8 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓ | Exempté
2050-08 | 2050 | 8 | Administration | 5 | 0 | 1 | 0 | ✓
2050-09 | 2050 | 9 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-09 | 2050 | 9 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2050-09 | 2050 | 9 | Administration | 5 | 0 | 1 | 0 | ✓
2050-10 | 2050 | 10 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-10 | 2050 | 10 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2050-10 | 2050 | 10 | Administration | 5 | 0 | 1 | 0 | ✓
2050-11 | 2050 | 11 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-11 | 2050 | 11 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2050-11 | 2050 | 11 | Administration | 5 | 0 | 1 | 0 | ✓
2050-12 | 2050 | 12 | Sports | 15 | 1 | 3 | 0.066667 | ✓
2050-12 | 2050 | 12 | Enseignement | 26 | 1 | 5.2 | 0.038462 | ✓
2050-12 | 2050 | 12 | Administration | 5 | 0 | 1 | 0 | ✓

## disponibilite_pivot
category | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11 | 2027-12 | 2028-01 | 2028-02 | 2028-03 | 2028-04 | 2028-05 | 2028-06 | 2028-07 | 2028-08 | 2028-09 | 2028-10 | 2028-11 | 2028-12 | 2029-01 | 2029-02 | 2029-03 | 2029-04 | 2029-05 | 2029-06 | 2029-07 | 2029-08 | 2029-09 | 2029-10 | 2029-11 | 2029-12 | 2030-01 | 2030-02 | 2030-03 | 2030-04 | 2030-05 | 2030-06 | 2030-07 | 2030-08 | 2030-09 | 2030-10 | 2030-11 | 2030-12 | 2031-01 | 2031-02 | 2031-03 | 2031-04 | 2031-05 | 2031-06 | 2031-07 | 2031-08 | 2031-09 | 2031-10 | 2031-11 | 2031-12 | 2032-01 | 2032-02 | 2032-03 | 2032-04 | 2032-05 | 2032-06 | 2032-07 | 2032-08 | 2032-09 | 2032-10 | 2032-11 | 2032-12 | 2033-01 | 2033-02 | 2033-03 | 2033-04 | 2033-05 | 2033-06 | 2033-07 | 2033-08 | 2033-09 | 2033-10 | 2033-11 | 2033-12 | 2034-01 | 2034-02 | 2034-03 | 2034-04 | 2034-05 | 2034-06 | 2034-07 | 2034-08 | 2034-09 | 2034-10 | 2034-11 | 2034-12 | 2035-01 | 2035-02 | 2035-03 | 2035-04 | 2035-05 | 2035-06 | 2035-07 | 2035-08 | 2035-09 | 2035-10 | 2035-11 | 2035-12 | 2036-01 | 2036-02 | 2036-03 | 2036-04 | 2036-05 | 2036-06 | 2036-07 | 2036-08 | 2036-09 | 2036-10 | 2036-11 | 2036-12 | 2037-01 | 2037-02 | 2037-03 | 2037-04 | 2037-05 | 2037-06 | 2037-07 | 2037-08 | 2037-09 | 2037-10 | 2037-11 | 2037-12 | 2038-01 | 2038-02 | 2038-03 | 2038-04 | 2038-05 | 2038-06 | 2038-07 | 2038-08 | 2038-09 | 2038-10 | 2038-11 | 2038-12 | 2039-01 | 2039-02 | 2039-03 | 2039-04 | 2039-05 | 2039-06 | 2039-07 | 2039-08 | 2039-09 | 2039-10 | 2039-11 | 2039-12 | 2040-01 | 2040-02 | 2040-03 | 2040-04 | 2040-05 | 2040-06 | 2040-07 | 2040-08 | 2040-09 | 2040-10 | 2040-11 | 2040-12 | 2041-01 | 2041-02 | 2041-03 | 2041-04 | 2041-05 | 2041-06 | 2041-07 | 2041-08 | 2041-09 | 2041-10 | 2041-11 | 2041-12 | 2042-01 | 2042-02 | 2042-03 | 2042-04 | 2042-05 | 2042-06 | 2042-07 | 2042-08 | 2042-09 | 2042-10 | 2042-11 | 2042-12 | 2043-01 | 2043-02 | 2043-03 | 2043-04 | 2043-05 | 2043-06 | 2043-07 | 2043-08 | 2043-09 | 2043-10 | 2043-11 | 2043-12 | 2044-01 | 2044-02 | 2044-03 | 2044-04 | 2044-05 | 2044-06 | 2044-07 | 2044-08 | 2044-09 | 2044-10 | 2044-11 | 2044-12 | 2045-01 | 2045-02 | 2045-03 | 2045-04 | 2045-05 | 2045-06 | 2045-07 | 2045-08 | 2045-09 | 2045-10 | 2045-11 | 2045-12 | 2046-01 | 2046-02 | 2046-03 | 2046-04 | 2046-05 | 2046-06 | 2046-07 | 2046-08 | 2046-09 | 2046-10 | 2046-11 | 2046-12 | 2047-01 | 2047-02 | 2047-03 | 2047-04 | 2047-05 | 2047-06 | 2047-07 | 2047-08 | 2047-09 | 2047-10 | 2047-11 | 2047-12 | 2048-01 | 2048-02 | 2048-03 | 2048-04 | 2048-05 | 2048-06 | 2048-07 | 2048-08 | 2048-09 | 2048-10 | 2048-11 | 2048-12 | 2049-01 | 2049-02 | 2049-03 | 2049-04 | 2049-05 | 2049-06 | 2049-07 | 2049-08 | 2049-09 | 2049-10 | 2049-11 | 2049-12 | 2050-01 | 2050-02 | 2050-03 | 2050-04 | 2050-05 | 2050-06 | 2050-07 | 2050-08 | 2050-09 | 2050-10 | 2050-11 | 2050-12
Administration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enseignement | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sports | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Feuil1
category | Administration | Admin(%) | Enseignement | Enseignement(%) | Sports | Sports (%)
2026-01 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2026-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-06 | 0 | 0 | 0 | 0 | 0 | 0
2026-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2026-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-01 | 0 | 0 | 2 | 7.6923 | 0 | 0
2027-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2027-07 | 0 | 0 | 2 | 7.6923 | 0 | 0
2027-08 | 0 | 0 | 2 | 7.6923 | 0 | 0
2027-09 | 0 | 0 | 2 | 7.6923 | 1 | 6.6667
2027-10 | 0 | 0 | 2 | 7.6923 | 1 | 6.6667
2027-11 | 0 | 0 | 2 | 7.6923 | 0 | 0
2027-12 | 0 | 0 | 2 | 7.6923 | 0 | 0
2028-01 | 0 | 0 | 2 | 7.6923 | 0 | 0
2028-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2028-03 | 0 | 0 | 0 | 0 | 0 | 0
2028-04 | 0 | 0 | 0 | 0 | 0 | 0
2028-05 | 0 | 0 | 0 | 0 | 0 | 0
2028-06 | 0 | 0 | 0 | 0 | 0 | 0
2028-07 | 0 | 0 | 0 | 0 | 0 | 0
2028-08 | 0 | 0 | 0 | 0 | 0 | 0
2028-09 | 0 | 0 | 0 | 0 | 0 | 0
2028-10 | 0 | 0 | 0 | 0 | 0 | 0
2028-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2028-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-05 | 0 | 0 | 0 | 0 | 0 | 0
2029-06 | 0 | 0 | 0 | 0 | 0 | 0
2029-07 | 0 | 0 | 0 | 0 | 0 | 0
2029-08 | 0 | 0 | 0 | 0 | 0 | 0
2029-09 | 0 | 0 | 0 | 0 | 0 | 0
2029-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2029-12 | 0 | 0 | 0 | 0 | 0 | 0
2030-01 | 0 | 0 | 0 | 0 | 0 | 0
2030-02 | 0 | 0 | 0 | 0 | 0 | 0
2030-03 | 0 | 0 | 0 | 0 | 0 | 0
2030-04 | 0 | 0 | 0 | 0 | 0 | 0
2030-05 | 0 | 0 | 0 | 0 | 0 | 0
2030-06 | 0 | 0 | 0 | 0 | 0 | 0
2030-07 | 0 | 0 | 0 | 0 | 0 | 0
2030-08 | 0 | 0 | 0 | 0 | 0 | 0
2030-09 | 0 | 0 | 0 | 0 | 0 | 0
2030-10 | 0 | 0 | 0 | 0 | 0 | 0
2030-11 | 0 | 0 | 0 | 0 | 0 | 0
2030-12 | 1 | 20 | 0 | 0 | 0 | 0
2031-01 | 0 | 0 | 0 | 0 | 0 | 0
2031-02 | 0 | 0 | 0 | 0 | 0 | 0
2031-03 | 0 | 0 | 0 | 0 | 0 | 0
2031-04 | 0 | 0 | 0 | 0 | 0 | 0
2031-05 | 0 | 0 | 0 | 0 | 0 | 0
2031-06 | 0 | 0 | 0 | 0 | 0 | 0
2031-07 | 0 | 0 | 0 | 0 | 0 | 0
2031-08 | 0 | 0 | 0 | 0 | 0 | 0
2031-09 | 0 | 0 | 0 | 0 | 0 | 0
2031-10 | 0 | 0 | 0 | 0 | 0 | 0
2031-11 | 0 | 0 | 0 | 0 | 0 | 0
2031-12 | 0 | 0 | 0 | 0 | 0 | 0
2032-01 | 0 | 0 | 0 | 0 | 0 | 0
2032-02 | 0 | 0 | 0 | 0 | 0 | 0
2032-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2032-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2032-05 | 0 | 0 | 0 | 0 | 0 | 0
2032-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2032-07 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2032-08 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2032-09 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2032-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2032-11 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2032-12 | 0 | 0 | 2 | 7.6923 | 1 | 6.6667
2033-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2033-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2034-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2034-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2034-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2034-04 | 0 | 0 | 0 | 0 | 0 | 0
2034-05 | 0 | 0 | 0 | 0 | 0 | 0
2034-06 | 0 | 0 | 0 | 0 | 0 | 0
2034-07 | 0 | 0 | 0 | 0 | 0 | 0
2034-08 | 0 | 0 | 0 | 0 | 0 | 0
2034-09 | 0 | 0 | 0 | 0 | 0 | 0
2034-10 | 0 | 0 | 0 | 0 | 0 | 0
2034-11 | 0 | 0 | 0 | 0 | 0 | 0
2034-12 | 0 | 0 | 0 | 0 | 0 | 0
2035-01 | 0 | 0 | 0 | 0 | 0 | 0
2035-02 | 0 | 0 | 0 | 0 | 0 | 0
2035-03 | 0 | 0 | 0 | 0 | 0 | 0
2035-04 | 0 | 0 | 0 | 0 | 0 | 0
2035-05 | 0 | 0 | 0 | 0 | 0 | 0
2035-06 | 0 | 0 | 0 | 0 | 0 | 0
2035-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2035-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2035-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2035-10 | 0 | 0 | 2 | 7.6923 | 0 | 0
2035-11 | 0 | 0 | 2 | 7.6923 | 0 | 0
2035-12 | 0 | 0 | 2 | 7.6923 | 0 | 0
2036-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2036-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2036-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2036-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2036-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2036-06 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-07 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-08 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-09 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-10 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-11 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2036-12 | 1 | 20 | 1 | 3.8462 | 2 | 13.3333
2037-01 | 1 | 20 | 1 | 3.8462 | 1 | 6.6667
2037-02 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2037-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2037-04 | 0 | 0 | 0 | 0 | 0 | 0
2037-05 | 0 | 0 | 0 | 0 | 0 | 0
2037-06 | 0 | 0 | 0 | 0 | 0 | 0
2037-07 | 0 | 0 | 0 | 0 | 0 | 0
2037-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2037-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2037-10 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2037-11 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2037-12 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2038-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-05 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2038-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2038-09 | 0 | 0 | 2 | 7.6923 | 0 | 0
2038-10 | 0 | 0 | 4 | 15.3846 | 0 | 0
2038-11 | 0 | 0 | 4 | 15.3846 | 0 | 0
2038-12 | 0 | 0 | 3 | 11.5385 | 1 | 6.6667
2039-01 | 0 | 0 | 2 | 7.6923 | 0 | 0
2039-02 | 0 | 0 | 2 | 7.6923 | 0 | 0
2039-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-09 | 0 | 0 | 0 | 0 | 0 | 0
2039-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2039-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2040-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2040-02 | 1 | 20 | 1 | 3.8462 | 0 | 0
2040-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2040-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2040-05 | 0 | 0 | 0 | 0 | 0 | 0
2040-06 | 0 | 0 | 0 | 0 | 0 | 0
2040-07 | 0 | 0 | 0 | 0 | 0 | 0
2040-08 | 1 | 20 | 0 | 0 | 0 | 0
2040-09 | 1 | 20 | 0 | 0 | 0 | 0
2040-10 | 1 | 20 | 0 | 0 | 0 | 0
2040-11 | 1 | 20 | 0 | 0 | 0 | 0
2040-12 | 1 | 20 | 0 | 0 | 0 | 0
2041-01 | 1 | 20 | 0 | 0 | 0 | 0
2041-02 | 1 | 20 | 2 | 7.6923 | 0 | 0
2041-03 | 1 | 20 | 0 | 0 | 0 | 0
2041-04 | 1 | 20 | 0 | 0 | 0 | 0
2041-05 | 1 | 20 | 0 | 0 | 0 | 0
2041-06 | 1 | 20 | 0 | 0 | 0 | 0
2041-07 | 1 | 20 | 0 | 0 | 0 | 0
2041-08 | 1 | 20 | 1 | 3.8462 | 0 | 0
2041-09 | 1 | 20 | 1 | 3.8462 | 0 | 0
2041-10 | 1 | 20 | 1 | 3.8462 | 0 | 0
2041-11 | 1 | 20 | 1 | 3.8462 | 0 | 0
2041-12 | 1 | 20 | 1 | 3.8462 | 1 | 6.6667
2042-01 | 1 | 20 | 1 | 3.8462 | 1 | 6.6667
2042-02 | 0 | 0 | 1 | 3.8462 | 2 | 13.3333
2042-03 | 1 | 20 | 1 | 3.8462 | 2 | 13.3333
2042-04 | 1 | 20 | 1 | 3.8462 | 2 | 13.3333
2042-05 | 0 | 0 | 2 | 7.6923 | 0 | 0
2042-06 | 0 | 0 | 2 | 7.6923 | 0 | 0
2042-07 | 0 | 0 | 2 | 7.6923 | 0 | 0
2042-08 | 0 | 0 | 3 | 11.5385 | 0 | 0
2042-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2042-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2042-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2042-12 | 0 | 0 | 2 | 7.6923 | 0 | 0
2043-01 | 0 | 0 | 2 | 7.6923 | 0 | 0
2043-02 | 0 | 0 | 0 | 0 | 0 | 0
2043-03 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-04 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-05 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-06 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-07 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-08 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-09 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-10 | 0 | 0 | 0 | 0 | 1 | 6.6667
2043-11 | 0 | 0 | 0 | 0 | 2 | 13.3333
2043-12 | 0 | 0 | 0 | 0 | 1 | 6.6667
2044-01 | 0 | 0 | 0 | 0 | 1 | 6.6667
2044-02 | 0 | 0 | 0 | 0 | 1 | 6.6667
2044-03 | 0 | 0 | 0 | 0 | 2 | 13.3333
2044-04 | 0 | 0 | 0 | 0 | 0 | 0
2044-05 | 0 | 0 | 0 | 0 | 0 | 0
2044-06 | 0 | 0 | 0 | 0 | 0 | 0
2044-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2044-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2044-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2044-10 | 0 | 0 | 2 | 7.6923 | 0 | 0
2044-11 | 0 | 0 | 2 | 7.6923 | 0 | 0
2044-12 | 1 | 20 | 1 | 3.8462 | 0 | 0
2045-01 | 1 | 20 | 1 | 3.8462 | 0 | 0
2045-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-03 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-04 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2045-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-02 | 0 | 0 | 0 | 0 | 0 | 0
2046-03 | 0 | 0 | 0 | 0 | 0 | 0
2046-04 | 0 | 0 | 0 | 0 | 0 | 0
2046-05 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-06 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-07 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-08 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-09 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2046-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2047-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2047-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2047-03 | 1 | 20 | 1 | 3.8462 | 0 | 0
2047-04 | 1 | 20 | 1 | 3.8462 | 1 | 6.6667
2047-05 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2047-06 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2047-07 | 0 | 0 | 0 | 0 | 1 | 6.6667
2047-08 | 0 | 0 | 0 | 0 | 1 | 6.6667
2047-09 | 0 | 0 | 0 | 0 | 1 | 6.6667
2047-10 | 0 | 0 | 0 | 0 | 1 | 6.6667
2047-11 | 0 | 0 | 0 | 0 | 0 | 0
2047-12 | 0 | 0 | 0 | 0 | 0 | 0
2048-01 | 0 | 0 | 0 | 0 | 2 | 13.3333
2048-02 | 0 | 0 | 1 | 3.8462 | 2 | 13.3333
2048-03 | 0 | 0 | 1 | 3.8462 | 3 | 20
2048-04 | 0 | 0 | 0 | 0 | 0 | 0
2048-05 | 0 | 0 | 0 | 0 | 0 | 0
2048-06 | 0 | 0 | 0 | 0 | 0 | 0
2048-07 | 0 | 0 | 0 | 0 | 0 | 0
2048-08 | 0 | 0 | 0 | 0 | 0 | 0
2048-09 | 0 | 0 | 0 | 0 | 0 | 0
2048-10 | 0 | 0 | 0 | 0 | 0 | 0
2048-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2048-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2049-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2049-02 | 0 | 0 | 1 | 3.8462 | 0 | 0
2049-03 | 0 | 0 | 2 | 7.6923 | 0 | 0
2049-04 | 0 | 0 | 3 | 11.5385 | 0 | 0
2049-05 | 0 | 0 | 3 | 11.5385 | 0 | 0
2049-06 | 0 | 0 | 3 | 11.5385 | 0 | 0
2049-07 | 0 | 0 | 2 | 7.6923 | 0 | 0
2049-08 | 0 | 0 | 2 | 7.6923 | 0 | 0
2049-09 | 0 | 0 | 2 | 7.6923 | 0 | 0
2049-10 | 0 | 0 | 1 | 3.8462 | 0 | 0
2049-11 | 0 | 0 | 1 | 3.8462 | 0 | 0
2049-12 | 0 | 0 | 1 | 3.8462 | 0 | 0
2050-01 | 0 | 0 | 1 | 3.8462 | 0 | 0
2050-02 | 0 | 0 | 0 | 0 | 0 | 0
2050-03 | 0 | 0 | 0 | 0 | 0 | 0
2050-04 | 0 | 0 | 0 | 0 | 1 | 6.6667
2050-05 | 0 | 0 | 0 | 0 | 1 | 6.6667
2050-06 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-07 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-08 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-09 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-10 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-11 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
2050-12 | 0 | 0 | 1 | 3.8462 | 1 | 6.6667
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1
category | Administration |  | Enseignement |  | Sports
2026-01 | 0 |  | 1 |  | 1
2026-02 | 0 |  | 1 |  | 0
2026-03 | 0 |  | 1 |  | 0
2026-04 | 0 |  | 1 |  | 0
2026-05 | 0 |  | 1 |  | 0
2026-06 | 0 |  | 0 |  | 0
2026-07 | 0 |  | 1 |  | 0
2026-08 | 0 |  | 1 |  | 0
2026-09 | 0 |  | 1 |  | 0
2026-10 | 0 |  | 1 |  | 0
2026-11 | 0 |  | 1 |  | 0
2026-12 | 0 |  | 1 |  | 0
2027-01 | 0 |  | 2 |  | 0
2027-02 | 0 |  | 1 |  | 0
2027-03 | 0 |  | 1 |  | 0
2027-04 | 0 |  | 1 |  | 0
2027-05 | 0 |  | 1 |  | 0
2027-06 | 0 |  | 1 |  | 0
2027-07 | 0 |  | 2 |  | 0
2027-08 | 0 |  | 2 |  | 0
2027-09 | 0 |  | 2 |  | 1
2027-10 | 0 |  | 2 |  | 1
2027-11 | 0 |  | 2 |  | 0
2027-12 | 0 |  | 2 |  | 0
2028-01 | 0 |  | 2 |  | 0
2028-02 | 0 |  | 1 |  | 0
2028-03 | 0 |  | 0 |  | 0
2028-04 | 0 |  | 0 |  | 0
2028-05 | 0 |  | 0 |  | 0
2028-06 | 0 |  | 0 |  | 0
2028-07 | 0 |  | 0 |  | 0
2028-08 | 0 |  | 0 |  | 0
2028-09 | 0 |  | 0 |  | 0
2028-10 | 0 |  | 0 |  | 0
2028-11 | 0 |  | 1 |  | 0
2028-12 | 0 |  | 1 |  | 0
2029-01 | 0 |  | 1 |  | 0
2029-02 | 0 |  | 1 |  | 0
2029-03 | 0 |  | 1 |  | 0
2029-04 | 0 |  | 1 |  | 0
2029-05 | 0 |  | 0 |  | 0
2029-06 | 0 |  | 0 |  | 0
2029-07 | 0 |  | 0 |  | 0
2029-08 | 0 |  | 0 |  | 0
2029-09 | 0 |  | 0 |  | 0
2029-10 | 0 |  | 1 |  | 0
2029-11 | 0 |  | 1 |  | 0
2029-12 | 0 |  | 0 |  | 0
2030-01 | 0 |  | 0 |  | 0
2030-02 | 0 |  | 0 |  | 0
2030-03 | 0 |  | 0 |  | 0
2030-04 | 0 |  | 0 |  | 0
2030-05 | 0 |  | 0 |  | 0
2030-06 | 0 |  | 0 |  | 0
2030-07 | 0 |  | 0 |  | 0
2030-08 | 0 |  | 0 |  | 0
2030-09 | 0 |  | 0 |  | 0
2030-10 | 0 |  | 0 |  | 0
2030-11 | 0 |  | 0 |  | 0
2030-12 | 1 |  | 0 |  | 0
2031-01 | 0 |  | 0 |  | 0
2031-02 | 0 |  | 0 |  | 0
2031-03 | 0 |  | 0 |  | 0
2031-04 | 0 |  | 0 |  | 0
2031-05 | 0 |  | 0 |  | 0
2031-06 | 0 |  | 0 |  | 0
2031-07 | 0 |  | 0 |  | 0
2031-08 | 0 |  | 0 |  | 0
2031-09 | 0 |  | 0 |  | 0
2031-10 | 0 |  | 0 |  | 0
2031-11 | 0 |  | 0 |  | 0
2031-12 | 0 |  | 0 |  | 0
2032-01 | 0 |  | 0 |  | 0
2032-02 | 0 |  | 0 |  | 0
2032-03 | 0 |  | 1 |  | 0
2032-04 | 0 |  | 1 |  | 0
2032-05 | 0 |  | 0 |  | 0
2032-06 | 0 |  | 1 |  | 0
2032-07 | 0 |  | 1 |  | 1
2032-08 | 0 |  | 1 |  | 1
2032-09 | 0 |  | 1 |  | 1
2032-10 | 0 |  | 1 |  | 0
2032-11 | 0 |  | 1 |  | 1
2032-12 | 0 |  | 2 |  | 1
2033-01 | 0 |  | 1 |  | 0
2033-02 | 0 |  | 1 |  | 0
2033-03 | 0 |  | 1 |  | 0
2033-04 | 0 |  | 1 |  | 0
2033-05 | 0 |  | 1 |  | 0
2033-06 | 0 |  | 1 |  | 0
2033-07 | 0 |  | 1 |  | 0
2033-08 | 0 |  | 1 |  | 0
2033-09 | 0 |  | 1 |  | 0
2033-10 | 0 |  | 1 |  | 0
2033-11 | 0 |  | 1 |  | 0
2033-12 | 0 |  | 1 |  | 0
2034-01 | 0 |  | 1 |  | 0
2034-02 | 0 |  | 1 |  | 0
2034-03 | 0 |  | 1 |  | 0
2034-04 | 0 |  | 0 |  | 0
2034-05 | 0 |  | 0 |  | 0
2034-06 | 0 |  | 0 |  | 0
2034-07 | 0 |  | 0 |  | 0
2034-08 | 0 |  | 0 |  | 0
2034-09 | 0 |  | 0 |  | 0
2034-10 | 0 |  | 0 |  | 0
2034-11 | 0 |  | 0 |  | 0
2034-12 | 0 |  | 0 |  | 0
2035-01 | 0 |  | 0 |  | 0
2035-02 | 0 |  | 0 |  | 0
2035-03 | 0 |  | 0 |  | 0
2035-04 | 0 |  | 0 |  | 0
2035-05 | 0 |  | 0 |  | 0
2035-06 | 0 |  | 0 |  | 0
2035-07 | 0 |  | 1 |  | 0
2035-08 | 0 |  | 1 |  | 0
2035-09 | 0 |  | 1 |  | 0
2035-10 | 0 |  | 2 |  | 0
2035-11 | 0 |  | 2 |  | 0
2035-12 | 0 |  | 2 |  | 0
2036-01 | 0 |  | 1 |  | 0
2036-02 | 0 |  | 1 |  | 0
2036-03 | 0 |  | 1 |  | 0
2036-04 | 0 |  | 1 |  | 0
2036-05 | 0 |  | 1 |  | 0
2036-06 | 0 |  | 1 |  | 1
2036-07 | 0 |  | 1 |  | 1
2036-08 | 0 |  | 1 |  | 1
2036-09 | 0 |  | 1 |  | 1
2036-10 | 0 |  | 1 |  | 1
2036-11 | 0 |  | 1 |  | 1
2036-12 | 1 |  | 1 |  | 2
2037-01 | 1 |  | 1 |  | 1
2037-02 | 0 |  | 1 |  | 1
2037-03 | 0 |  | 1 |  | 0
2037-04 | 0 |  | 0 |  | 0
2037-05 | 0 |  | 0 |  | 0
2037-06 | 0 |  | 0 |  | 0
2037-07 | 0 |  | 0 |  | 0
2037-08 | 0 |  | 1 |  | 0
2037-09 | 0 |  | 1 |  | 0
2037-10 | 0 |  | 1 |  | 1
2037-11 | 0 |  | 1 |  | 1
2037-12 | 0 |  | 1 |  | 1
2038-01 | 0 |  | 1 |  | 0
2038-02 | 0 |  | 1 |  | 0
2038-03 | 0 |  | 1 |  | 0
2038-04 | 0 |  | 1 |  | 0
2038-05 | 0 |  | 1 |  | 1
2038-06 | 0 |  | 1 |  | 0
2038-07 | 0 |  | 1 |  | 0
2038-08 | 0 |  | 1 |  | 0
2038-09 | 0 |  | 2 |  | 0
2038-10 | 0 |  | 4 |  | 0
2038-11 | 0 |  | 4 |  | 0
2038-12 | 0 |  | 3 |  | 1
2039-01 | 0 |  | 2 |  | 0
2039-02 | 0 |  | 2 |  | 0
2039-03 | 0 |  | 1 |  | 0
2039-04 | 0 |  | 1 |  | 0
2039-05 | 0 |  | 1 |  | 0
2039-06 | 0 |  | 1 |  | 0
2039-07 | 0 |  | 1 |  | 0
2039-08 | 0 |  | 1 |  | 0
2039-09 | 0 |  | 0 |  | 0
2039-10 | 0 |  | 1 |  | 0
2039-11 | 0 |  | 1 |  | 0
2039-12 | 0 |  | 1 |  | 0
2040-01 | 0 |  | 1 |  | 0
2040-02 | 1 |  | 1 |  | 0
2040-03 | 0 |  | 1 |  | 0
2040-04 | 0 |  | 1 |  | 0
2040-05 | 0 |  | 0 |  | 0
2040-06 | 0 |  | 0 |  | 0
2040-07 | 0 |  | 0 |  | 0
2040-08 | 1 |  | 0 |  | 0
2040-09 | 1 |  | 0 |  | 0
2040-10 | 1 |  | 0 |  | 0
2040-11 | 1 |  | 0 |  | 0
2040-12 | 1 |  | 0 |  | 0
2041-01 | 1 |  | 0 |  | 0
2041-02 | 1 |  | 2 |  | 0
2041-03 | 1 |  | 0 |  | 0
2041-04 | 1 |  | 0 |  | 0
2041-05 | 1 |  | 0 |  | 0
2041-06 | 1 |  | 0 |  | 0
2041-07 | 1 |  | 0 |  | 0
2041-08 | 1 |  | 1 |  | 0
2041-09 | 1 |  | 1 |  | 0
2041-10 | 1 |  | 1 |  | 0
2041-11 | 1 |  | 1 |  | 0
2041-12 | 1 |  | 1 |  | 1
2042-01 | 1 |  | 1 |  | 1
2042-02 | 0 |  | 1 |  | 2
2042-03 | 1 |  | 1 |  | 2
2042-04 | 1 |  | 1 |  | 2
2042-05 | 0 |  | 2 |  | 0
2042-06 | 0 |  | 2 |  | 0
2042-07 | 0 |  | 2 |  | 0
2042-08 | 0 |  | 3 |  | 0
2042-09 | 0 |  | 1 |  | 0
2042-10 | 0 |  | 1 |  | 0
2042-11 | 0 |  | 1 |  | 0
2042-12 | 0 |  | 2 |  | 0
2043-01 | 0 |  | 2 |  | 0
2043-02 | 0 |  | 0 |  | 0
2043-03 | 0 |  | 0 |  | 1
2043-04 | 0 |  | 0 |  | 1
2043-05 | 0 |  | 0 |  | 1
2043-06 | 0 |  | 0 |  | 1
2043-07 | 0 |  | 0 |  | 1
2043-08 | 0 |  | 0 |  | 1
2043-09 | 0 |  | 0 |  | 1
2043-10 | 0 |  | 0 |  | 1
2043-11 | 0 |  | 0 |  | 2
2043-12 | 0 |  | 0 |  | 1
2044-01 | 0 |  | 0 |  | 1
2044-02 | 0 |  | 0 |  | 1
2044-03 | 0 |  | 0 |  | 2
2044-04 | 0 |  | 0 |  | 0
2044-05 | 0 |  | 0 |  | 0
2044-06 | 0 |  | 0 |  | 0
2044-07 | 0 |  | 1 |  | 0
2044-08 | 0 |  | 1 |  | 0
2044-09 | 0 |  | 1 |  | 0
2044-10 | 0 |  | 2 |  | 0
2044-11 | 0 |  | 2 |  | 0
2044-12 | 1 |  | 1 |  | 0
2045-01 | 1 |  | 1 |  | 0
2045-02 | 0 |  | 1 |  | 0
2045-03 | 0 |  | 1 |  | 0
2045-04 | 0 |  | 1 |  | 0
2045-05 | 0 |  | 1 |  | 0
2045-06 | 0 |  | 1 |  | 0
2045-07 | 0 |  | 1 |  | 0
2045-08 | 0 |  | 1 |  | 0
2045-09 | 0 |  | 1 |  | 0
2045-10 | 0 |  | 1 |  | 0
2045-11 | 0 |  | 1 |  | 0
2045-12 | 0 |  | 1 |  | 0
2046-01 | 0 |  | 1 |  | 0
2046-02 | 0 |  | 0 |  | 0
2046-03 | 0 |  | 0 |  | 0
2046-04 | 0 |  | 0 |  | 0
2046-05 | 0 |  | 1 |  | 0
2046-06 | 0 |  | 1 |  | 0
2046-07 | 0 |  | 1 |  | 0
2046-08 | 0 |  | 1 |  | 0
2046-09 | 0 |  | 1 |  | 0
2046-10 | 0 |  | 1 |  | 0
2046-11 | 0 |  | 1 |  | 0
2046-12 | 0 |  | 1 |  | 0
2047-01 | 0 |  | 1 |  | 0
2047-02 | 0 |  | 1 |  | 0
2047-03 | 1 |  | 1 |  | 0
2047-04 | 1 |  | 1 |  | 1
2047-05 | 0 |  | 1 |  | 1
2047-06 | 0 |  | 1 |  | 1
2047-07 | 0 |  | 0 |  | 1
2047-08 | 0 |  | 0 |  | 1
2047-09 | 0 |  | 0 |  | 1
2047-10 | 0 |  | 0 |  | 1
2047-11 | 0 |  | 0 |  | 0
2047-12 | 0 |  | 0 |  | 0
2048-01 | 0 |  | 0 |  | 2
2048-02 | 0 |  | 1 |  | 2
2048-03 | 0 |  | 1 |  | 3
2048-04 | 0 |  | 0 |  | 0
2048-05 | 0 |  | 0 |  | 0
2048-06 | 0 |  | 0 |  | 0
2048-07 | 0 |  | 0 |  | 0
2048-08 | 0 |  | 0 |  | 0
2048-09 | 0 |  | 0 |  | 0
2048-10 | 0 |  | 0 |  | 0
2048-11 | 0 |  | 1 |  | 0
2048-12 | 0 |  | 1 |  | 0
2049-01 | 0 |  | 1 |  | 0
2049-02 | 0 |  | 1 |  | 0
2049-03 | 0 |  | 2 |  | 0
2049-04 | 0 |  | 3 |  | 0
2049-05 | 0 |  | 3 |  | 0
2049-06 | 0 |  | 3 |  | 0
2049-07 | 0 |  | 2 |  | 0
2049-08 | 0 |  | 2 |  | 0
2049-09 | 0 |  | 2 |  | 0
2049-10 | 0 |  | 1 |  | 0
2049-11 | 0 |  | 1 |  | 0
2049-12 | 0 |  | 1 |  | 0
2050-01 | 0 |  | 1 |  | 0
2050-02 | 0 |  | 0 |  | 0
2050-03 | 0 |  | 0 |  | 0
2050-04 | 0 |  | 0 |  | 1
2050-05 | 0 |  | 0 |  | 1
2050-06 | 0 |  | 1 |  | 1
2050-07 | 0 |  | 1 |  | 1
2050-08 | 0 |  | 1 |  | 1
2050-09 | 0 |  | 1 |  | 1
2050-10 | 0 |  | 1 |  | 1
2050-11 | 0 |  | 1 |  | 1
2050-12 | 0 |  | 1 |  | 1