## transitions
building | year | from_state | to_state | works_added | gain | cost
abri_bouliste | 2028 | none | abri_bouliste_simulation_1 | indoor_wall_isolation | 2.8965 | 9352.936
abri_bouliste | 2039 | abri_bouliste_simulation_1 | abri_bouliste_simulation_2 | roof_isolation | 2.8075 | 27243.124
abri_bouliste | 2040 | abri_bouliste_simulation_2 | abri_bouliste_simulation_4 | floor_isolation | 0.29666 | 10256.24
abri_bouliste | 2044 | abri_bouliste_simulation_4 | abri_bouliste_simulation_11 | window_replacement_DG | 0.086744 | 15241.82
accueil_de_loisirs_maternel_la_varenne | 2043 | none | accueil_de_loisirs_maternel_la_varenne_simulation_3 | roof_isolation | 1.7374 | 77747.4796
accueil_de_loisirs_maternel_la_varenne | 2050 | accueil_de_loisirs_maternel_la_varenne_simulation_3 | accueil_de_loisirs_maternel_la_varenne_simulation_14 | indoor_wall_isolation, window_replacement_TG, floor_isolation | 1.5824 | 163720.426
association_31_rue_gambetta | 2032 | none | association_31_rue_gambetta_simulation_1 | indoor_wall_isolation | 4.2973 | 28323.4
association_31_rue_gambetta | 2047 | association_31_rue_gambetta_simulation_1 | association_31_rue_gambetta_simulation_6 | window_replacement_DG, roof_isolation | 3.0283 | 138728.1
ateliers_municipaux_(ctm) | 2026 | none | ateliers_municipaux_(ctm)_simulation_8 | exterior_wall_isolation, roof_isolation, VMC_installation, system_installation | 662.7462 | 1635030.88
ateliers_municipaux_(ctm) | 2043 | ateliers_municipaux_(ctm)_simulation_8 | ateliers_municipaux_(ctm)_simulation_9 | window_replacement_DG | 13.1381 | 360526.58
base_de_canoe_kayak | 2028 | none | base_de_canoe_kayak_simulation_3 | indoor_wall_isolation, floor_isolation | 10.5499 | 12838.63
base_de_canoe_kayak | 2031 | base_de_canoe_kayak_simulation_3 | base_de_canoe_kayak_simulation_12 | roof_isolation | 3.0657 | 15193.07
bureaux_21_rue_des_sports | 2032 | none | bureaux_21_rue_des_sports_simulation_1 | indoor_wall_isolation | 1.3543 | 6953.943
bureaux_21_rue_des_sports | 2050 | bureaux_21_rue_des_sports_simulation_1 | bureaux_21_rue_des_sports_simulation_14 | window_replacement_DG, roof_isolation | 1.5062 | 36542.594
cdj_du_champy | 2038 | none | cdj_du_champy_simulation_12 | floor_isolation, VMC_installation | 8.7319 | 74831.111
cdj_du_champy | 2039 | cdj_du_champy_simulation_12 | cdj_du_champy_simulation_8 | indoor_wall_isolation, roof_isolation | 11.8223 | 91739.5433
cdj_du_pave_neuf | 2029 | none | cdj_du_pave_neuf_simulation_1 | indoor_wall_isolation | 9.0161 | 26123.4895
cdj_du_pave_neuf | 2040 | cdj_du_pave_neuf_simulation_1 | cdj_du_pave_neuf_simulation_3 | roof_isolation | 3.5453 | 38704.7689
cdj_du_pave_neuf | 2049 | cdj_du_pave_neuf_simulation_3 | cdj_du_pave_neuf_simulation_11 | floor_isolation, VMC_installation | 4.6319 | 91011.9026
centre_aquatique_les_nymphéas | 2032 | none | centre_aquatique_les_nymphéas_simulation_1 | floor_isolation | 63.5966 | 358316.0643
centre_horticole | 2040 | none | centre_horticole_simulation_3 | exterior_wall_isolation | 5.1057 | 76646.8955
centre_horticole | 2047 | centre_horticole_simulation_3 | centre_horticole_simulation_7 | roof_isolation | 1.4623 | 43254.3906
centre_horticole | 2048 | centre_horticole_simulation_7 | centre_horticole_simulation_15 | window_replacement_TG | 0.73115 | 63872.4129
cimetiere_nouveau | 2026 | none | cimetiere_nouveau_simulation_1 | indoor_wall_isolation | 2.1865 | 7940.6048
cimetiere_nouveau | 2035 | cimetiere_nouveau_simulation_1 | cimetiere_nouveau_simulation_5 | VMC_installation | 0.95655 | 9206.9625
cimetiere_nouveau | 2038 | cimetiere_nouveau_simulation_5 | cimetiere_nouveau_simulation_11 | floor_isolation, roof_isolation | 3.5756 | 22441.9712
cinéma_le_bijou | 2028 | none | cinéma_le_bijou_simulation_6 | floor_isolation, system_installation | 194.5148 | 164939.57
cinéma_le_bijou | 2046 | cinéma_le_bijou_simulation_6 | cinéma_le_bijou_simulation_7 | window_replacement_TG | 1.0253 | 70142.26
club_ricardo_bofil | 2042 | none | club_ricardo_bofil_simulation_2 | indoor_wall_isolation, floor_isolation | 3.2846 | 169732.8639
conservatoire_maurice_bacquet | 2027 | none | conservatoire_maurice_bacquet_simulation 5 | system_installation | 17.0812 | 28304.6
conservatoire_maurice_bacquet | 2034 | conservatoire_maurice_bacquet_simulation 5 | conservatoire_maurice_bacquet_simulation 8 | indoor_wall_isolation, floor_isolation | 8.4016 | 88764.93
conservatoire_maurice_bacquet | 2049 | conservatoire_maurice_bacquet_simulation 8 | conservatoire_maurice_bacquet_simulation 10 | VMC_installation | 11.9072 | 300366.61
creche_multi_accueil_des_farfadets | 2045 | none | creche_multi_accueil_des_farfadets_simulation_1 | indoor_wall_isolation | 1.1343 | 17569.17
creche_multi_accueil_des_farfadets | 2048 | creche_multi_accueil_des_farfadets_simulation_1 | creche_multi_accueil_des_farfadets_simulation_2 | floor_isolation | 2.0619 | 78647.19
crèche_et_halte_du_marnois | 2026 | none | crèche_et_halte_du_marnois_simulation_1 | indoor_wall_isolation | 23.2301 | 53206.98
crèche_et_halte_du_marnois | 2039 | crèche_et_halte_du_marnois_simulation_1 | crèche_et_halte_du_marnois_simulation_6 | roof_isolation | 42.7786 | 259016.22
crèche_et_halte_du_marnois | 2050 | crèche_et_halte_du_marnois_simulation_6 | crèche_et_halte_du_marnois_simulation_10 | window_replacement_DG, VMC_installation | 17.472 | 409173
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2027 | none | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | VMC_installation | 13.5994 | 44686.0192
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2028 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_3 | floor_isolation | 9.2553 | 33100.755
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2037 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_3 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_6 | indoor_wall_isolation | 2.1099 | 8284.2258
crèche_familiale_du_champy_-_relais_des_assistances_maternelles | 2040 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_6 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_7 | window_replacement_DG | 3.3722 | 49631
crèche_petit_prince | 2029 | none | crèche_petit_prince_simulation_3 | system_installation | 27.4445 | 11056.4207
crèche_petit_prince | 2044 | crèche_petit_prince_simulation_3 | crèche_petit_prince_simulation_7 | exterior_wall_isolation, window_replacement_TG | 4.1057 | 443046.5793
crèche_robert_debré | 2026 | none | crèche_robert_debré_simulation_8 | system_installation | 64.6101 | 9273.1738
crèche_robert_debré | 2048 | crèche_robert_debré_simulation_8 | crèche_robert_debré_simulation_9 | indoor_wall_isolation, roof_isolation, VMC_installation | -51.9201 | 209457.5362
crèche_robert_debré | 2049 | crèche_robert_debré_simulation_9 | crèche_robert_debré_simulation_10 | window_replacement_DG | 52.6952 | 282935.1
déchèterie_municipale | 2028 | none | déchèterie_municipale_simulation_1 | indoor_wall_isolation | 1.9923 | 6735.6568
déchèterie_municipale | 2034 | déchèterie_municipale_simulation_1 | déchèterie_municipale_simulation_4 | floor_isolation, roof_isolation | 1.762 | 15140.4638
déchèterie_municipale | 2045 | déchèterie_municipale_simulation_4 | déchèterie_municipale_simulation_11 | VMC_installation | 0.024817 | 7660.8159
emaus_1_et__2 | 2036 | none | emaus_1_et__2_simulation_1 | indoor_wall_isolation | 7.8305 | 29519.2555
emaus_1_et__2 | 2050 | emaus_1_et__2_simulation_1 | emaus_1_et__2_simulation_15 | window_replacement_DG, floor_isolation, roof_isolation | 7.4069 | 199575.0624
espace_michel_simon | 2037 | none | espace_michel_simon_simulation 4 | window_replacement_DG | 356.1949 | 1734957.675
groupe_scolaire_des_hauts_bâtons | 2030 | none | groupe_scolaire_des_hauts_bâtons_simulation_7 | exterior_wall_isolation, roof_isolation, system_installation | 243.0268 | 573223.7845
groupe_scolaire_des_hauts_bâtons | 2044 | groupe_scolaire_des_hauts_bâtons_simulation_7 | groupe_scolaire_des_hauts_bâtons_simulation_9 | window_replacement_DG, VMC_installation | 0.00058 | 866719.6855
groupe_scolaire_les_coteaux | 2027 | none | groupe_scolaire_les_coteaux_simulation_13 | exterior_wall_isolation, roof_isolation | 361.2195 | 649628.8
groupe_scolaire_les_richardets | 2029 | none | groupe_scolaire_les_richardets_simulation_1 | exterior_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation | 328.6735 | 818360.552
groupe_scolaire_paul_serelle | 2028 | none | groupe_scolaire_paul_serelle_simulation_1 | exterior_wall_isolation, floor_isolation, roof_isolation | 322.3713 | 573049.868
groupe_scolaire_robert_desnos | 2030 | none | groupe_scolaire_robert_desnos_simulation_7 | indoor_wall_isolation, roof_isolation, system_installation | 210.1521 | 307702
groupe_scolaire_robert_desnos | 2048 | groupe_scolaire_robert_desnos_simulation_7 | groupe_scolaire_robert_desnos_simulation_10 | window_replacement_DG, VMC_installation | 29.9782 | 842292.7981
gs_alex_dumas | 2027 | none | gs_alex_dumas_simulation 3 | system_installation | 28.5418 | 26071.4
gs_alex_dumas | 2035 | gs_alex_dumas_simulation 3 | gs_alex_dumas_simulation 10 | exterior_wall_isolation, window_replacement_TG, VMC_installation | 159.8384 | 1370808.4
gs_celestin_freinet | 2029 | none | gs_celestin_freinet_simulation 2 | indoor_wall_isolation | 146.6642 | 103932.1125
gs_celestin_freinet | 2038 | gs_celestin_freinet_simulation 2 | gs_celestin_freinet_simulation 10 | window_replacement_DG, roof_isolation, VMC_installation | 160.9976 | 1567792.8
gs_clos_arche | 2029 | none | gs_clos_arche_simulation 2 | indoor_wall_isolation | 40.2285 | 100120.6125
gs_clos_arche | 2039 | gs_clos_arche_simulation 2 | gs_clos_arche_simulation 10 | window_replacement_DG, floor_isolation, VMC_installation, system_installation | 112.234 | 820634.2875
gs_clos_dambert | 2032 | none | gs_clos_dambert_simulation 6 | indoor_wall_isolation, VMC_installation | 112.276 | 774587.5375
gs_clos_dambert | 2043 | gs_clos_dambert_simulation 6 | gs_clos_dambert_simulation 10 | window_replacement_DG | 19.3743 | 968916.4625
gs_george_brassens | 2030 | none | gs_george_brassens_simulation 1 | exterior_wall_isolation | 137.8724 | 266245.38
gs_george_brassens | 2034 | gs_george_brassens_simulation 1 | gs_george_brassens_simulation 8 | window_replacement_TG, floor_isolation, roof_isolation | 132.4798 | 991739.25
gs_joliot_curie | 2029 | none | gs_joliot_curie_simulation 8 | exterior_wall_isolation, roof_isolation, system_installation | 619.4836 | 646264
gs_joliot_curie | 2033 | gs_joliot_curie_simulation 8 | gs_joliot_curie_simulation 9 | VMC_installation | 110.0215 | 659675.325
gs_jules_ferry | 2035 | none | gs_jules_ferry_simulation 5 | VMC_installation | 104.3237 | 579250
gs_jules_ferry | 2041 | gs_jules_ferry_simulation 5 | gs_jules_ferry_simulation 8 | exterior_wall_isolation, window_replacement_TG | 106.2295 | 1977043.6665
gs_jules_ferry | 2047 | gs_jules_ferry_simulation 8 | gs_jules_ferry_simulation 10 | floor_isolation, system_installation | 41.0739 | 301322.5235
gs_jules_verne | 2030 | none | gs_jules_verne_simulation 1 | exterior_wall_isolation | 214.8648 | 461835
gs_jules_verne | 2036 | gs_jules_verne_simulation 1 | gs_jules_verne_simulation 8 | window_replacement_DG, floor_isolation | 138.3516 | 1362949.4
gs_jules_verne | 2039 | gs_jules_verne_simulation 8 | gs_jules_verne_simulation 10 | VMC_installation | 66.5363 | 506550
gs_la_varenne | 2026 | none | gs_la_varenne_simulation 5 | system_installation | 63.5657 | 68502.2
gs_la_varenne | 2027 | gs_la_varenne_simulation 5 | gs_la_varenne_simulation 7 | exterior_wall_isolation, floor_isolation | 210.0771 | 702573.37
gs_la_varenne | 2046 | gs_la_varenne_simulation 7 | gs_la_varenne_simulation 10 | window_replacement_TG | 110.3279 | 1608871.8
gs_les_abeilles | 2028 | none | gs_les_abeilles_simulation 2 | exterior_wall_isolation | 168.5495 | 333163.476
gs_les_abeilles | 2033 | gs_les_abeilles_simulation 2 | gs_les_abeilles_simulation 10 | window_replacement_DG, roof_isolation, VMC_installation, system_installation | 143.9481 | 1334722.32
gs_les_charmilles | 2030 | none | gs_les_charmilles_simulation 1 | indoor_wall_isolation | 60.6552 | 81304.2
gs_les_charmilles | 2034 | gs_les_charmilles_simulation 1 | gs_les_charmilles_simulation 10 | window_replacement_DG, VMC_installation | 70.5526 | 654787.2
gs_les_noyers | 2027 | none | gs_les_noyers_simulation 2 | indoor_wall_isolation | 172.0379 | 176451.75
gs_les_noyers | 2031 | gs_les_noyers_simulation 2 | gs_les_noyers_simulation 8 | roof_isolation, system_installation | 202.312 | 763059.87
gs_les_noyers | 2047 | gs_les_noyers_simulation 8 | gs_les_noyers_simulation 10 | window_replacement_DG | 30.8863 | 860125.26
gs_les_yvris | 2028 | none | gs_les_yvris_simulation 1 | exterior_wall_isolation | 166.0759 | 355978.8
gs_les_yvris | 2040 | gs_les_yvris_simulation 1 | gs_les_yvris_simulation 10 | window_replacement_TG, VMC_installation | 142.2463 | 1335247
gs_van_gogh | 2028 | none | gs_van_gogh_simulation 1 | exterior_wall_isolation | 97.454 | 228505.05
gs_van_gogh | 2031 | gs_van_gogh_simulation 1 | gs_van_gogh_simulation 10 | window_replacement_DG, roof_isolation, system_installation | 116.7806 | 1085270.21
gymnase_champy | 2030 | none | gymnase_champy_simulation 8 | VMC_installation, system_installation | 123.8419 | 272250.12
gymnase_champy | 2044 | gymnase_champy_simulation 8 | gymnase_champy_simulation 10 | exterior_wall_isolation, window_replacement_TG | 15.5084 | 644591.3
gymnase_de_la_butte_verte | 2027 | none | gymnase_de_la_butte_verte_simulation_3 | system_installation | 156.9755 | 38515.4659
gymnase_de_la_butte_verte | 2042 | gymnase_de_la_butte_verte_simulation_3 | gymnase_de_la_butte_verte_simulation_8 | window_replacement_DG, VMC_installation | 26.3012 | 1436403.3141
gymnase_du_clos_de_l'arche | 2045 | none | gymnase_du_clos_de_l'arche_simulation_2 | window_replacement_TG | 14.8578 | 569215.2
gymnase_la_varenne | 2029 | none | gymnase_la_varenne_simulation 5 | VMC_installation | 124.4375 | 238050
gymnase_la_varenne | 2050 | gymnase_la_varenne_simulation 5 | gymnase_la_varenne_simulation 10 | window_replacement_DG, system_installation | 18.5831 | 599143.7
gymnase_les_coteaux | 2027 | none | gymnase_les_coteaux_simulation_1 | indoor_wall_isolation | 22.9096 | 57632.4
gymnase_les_coteaux | 2043 | gymnase_les_coteaux_simulation_1 | gymnase_les_coteaux_simulation_9 | window_replacement_DG, VMC_installation | 7.3322 | 329068.8
gymnase_les_yvris | 2026 | none | gymnase_les_yvris_simulation_1 | indoor_wall_isolation | 73.9174 | 69747.91
gymnase_les_yvris | 2032 | gymnase_les_yvris_simulation_1 | gymnase_les_yvris_simulation_7 | roof_isolation | 28.1184 | 142300.199
gymnase_les_yvris | 2034 | gymnase_les_yvris_simulation_7 | gymnase_les_yvris_simulation_10 | VMC_installation, system_installation | 75.2132 | 202020.741
gymnase_louison_bobet | 2026 | none | gymnase_louison_bobet_simulation 3 | VMC_installation | 73.597 | 133100
gymnase_louison_bobet | 2032 | gymnase_louison_bobet_simulation 3 | gymnase_louison_bobet_simulation 10 | exterior_wall_isolation, roof_isolation, system_installation | 128.3806 | 687649.2
hangar_bleu | 2028 | none | hangar_bleu_simulation_2 | indoor_wall_isolation | 45.0297 | 78050.2645
hangar_bleu | 2030 | hangar_bleu_simulation_2 | hangar_bleu_simulation_3 | system_installation | 9.125 | 10987.9855
hangar_bleu | 2036 | hangar_bleu_simulation_3 | hangar_bleu_simulation_9 | floor_isolation, roof_isolation | 29.4502 | 244860.4834
local_associatif_pablo_picasso | 2039 | none | local_associatif_pablo_picasso_simulation_1 | indoor_wall_isolation | 0.84129 | 9341.4003
local_associatif_pablo_picasso | 2048 | local_associatif_pablo_picasso_simulation_1 | local_associatif_pablo_picasso_simulation_7 | window_replacement_DG, floor_isolation | 0.21149 | 61884.0295
maison_de_la_jeunesse | 2027 | none | maison_de_la_jeunesse_simulation_1 | indoor_wall_isolation | 5.0858 | 15402.11
maison_de_la_jeunesse | 2034 | maison_de_la_jeunesse_simulation_1 | maison_de_la_jeunesse_simulation_9 | floor_isolation, roof_isolation, VMC_installation | 6.8878 | 45029.73
maison_des_services_publics_-_pimms | 2027 | none | maison_des_services_publics_-_pimms_simulation_1 | indoor_wall_isolation | 5.3192 | 12986.2461
maison_des_services_publics_-_pimms | 2038 | maison_des_services_publics_-_pimms_simulation_1 | maison_des_services_publics_-_pimms_simulation_2 | VMC_installation | 5.4189 | 57305.4742
maison_des_services_publics_-_pimms | 2042 | maison_des_services_publics_-_pimms_simulation_2 | maison_des_services_publics_-_pimms_simulation_13 | window_replacement_DG, floor_isolation | 6.8177 | 121344.0196
maison_des_syndicats | 2045 | none | maison_des_syndicats_simulation_1 | indoor_wall_isolation | 1.063 | 24740.71
maison_des_syndicats | 2048 | maison_des_syndicats_simulation_1 | maison_des_syndicats_simulation_11 | window_replacement_TG, roof_isolation | 3.3024 | 154332.99
maison_medicale_du_champy | 2048 | none | maison_medicale_du_champy_simulation_8 | exterior_wall_isolation, floor_isolation, VMC_installation | 8.7928 | 185904.2164
maison_medicale_du_champy | 2049 | maison_medicale_du_champy_simulation_8 | maison_medicale_du_champy_simulation_14 | window_replacement_DG | 1.5316 | 106073.1371
medecine_du_travail | 2037 | none | medecine_du_travail_simulation_3 | indoor_wall_isolation, VMC_installation | 6.846 | 54973.5944
medecine_du_travail | 2049 | medecine_du_travail_simulation_3 | medecine_du_travail_simulation_8 | floor_isolation, roof_isolation | 4.0602 | 71935.517
mille_club_des_yvris | 2037 | none | mille_club_des_yvris_simulation_8 | floor_isolation | 0.92327 | 16433.0726
mille_club_des_yvris | 2040 | mille_club_des_yvris_simulation_8 | mille_club_des_yvris_simulation_4 | indoor_wall_isolation, roof_isolation | 5.6874 | 57840.8024
mille_club_des_yvris | 2050 | mille_club_des_yvris_simulation_4 | mille_club_des_yvris_simulation_7 | window_replacement_DG | 2.5902 | 89197.1352
mpt_des_coteaux | 2037 | none | mpt_des_coteaux_simulation_8 | exterior_wall_isolation, floor_isolation, roof_isolation | 16.6601 | 120454.04
mpt_des_coteaux | 2046 | mpt_des_coteaux_simulation_8 | mpt_des_coteaux_simulation_13 | window_replacement_DG | 1.3479 | 82040.7321
mpt_du_champy | 2027 | none | mpt_du_champy_simulation_4 | system_installation | 33.1751 | 71000
mpt_du_champy | 2050 | mpt_du_champy_simulation_4 | mpt_du_champy_simulation_10 | indoor_wall_isolation, window_replacement_TG, VMC_installation | 2.5023 | 457551.452
mpt_jardin_des_sources_-_annexe_maison_pour_tous | 2045 | none | mpt_jardin_des_sources_-_annexe_maison_pour_tous_simulation_5 | exterior_wall_isolation, window_replacement_TG, floor_isolation | 10.3484 | 1230328.2724
mpt_la_varenne | 2028 | none | mpt_la_varenne_simulation 6 | VMC_installation | 16.3727 | 18800
mpt_la_varenne | 2038 | mpt_la_varenne_simulation 6 | mpt_la_varenne_simulation 10 | indoor_wall_isolation, window_replacement_TG, roof_isolation, system_installation | 43.1777 | 274952.19
mpt_les_richardets | 2040 | none | mpt_les_richardets_simulation_5 | VMC_installation | 10.9498 | 92083.26
mpt_les_richardets | 2042 | mpt_les_richardets_simulation_5 | mpt_les_richardets_simulation_10 | indoor_wall_isolation, window_replacement_DG, roof_isolation | 10.6557 | 238574.14
mpt_marcel_bou | 2029 | none | mpt_marcel_bou_simulation 1 | indoor_wall_isolation | 21.3504 | 27306.72
mpt_marcel_bou | 2037 | mpt_marcel_bou_simulation 1 | mpt_marcel_bou_simulation 9 | floor_isolation, roof_isolation, system_installation | 14.7883 | 62471.24
mpt_marcel_bou | 2040 | mpt_marcel_bou_simulation 9 | mpt_marcel_bou_simulation 10 | window_replacement_TG, VMC_installation | 12.2478 | 135533.18
multi_accueil_jean_piaget | 2036 | none | multi_accueil_jean_piaget_simulation_6 | indoor_wall_isolation, floor_isolation, VMC_installation | 65.1495 | 275781.3159
multi_accueil_jean_piaget | 2040 | multi_accueil_jean_piaget_simulation_6 | multi_accueil_jean_piaget_simulation_7 | window_replacement_DG | 20.6546 | 198630.0299
noisy_connecte | 2027 | none | noisy_connecte_simulation_3 | floor_isolation | 3.1919 | 8160.415
noisy_connecte | 2029 | noisy_connecte_simulation_3 | noisy_connecte_simulation_2 | indoor_wall_isolation | 5.1009 | 5624.585
noisy_connecte | 2039 | noisy_connecte_simulation_2 | noisy_connecte_simulation_9 | window_replacement_TG | 2.2994 | 23817
salle_de_boxe | 2030 | none | salle_de_boxe_simulation_2 | indoor_wall_isolation, floor_isolation | 9.7207 | 26094.5999
salle_de_boxe | 2036 | salle_de_boxe_simulation_2 | salle_de_boxe_simulation_5 | VMC_installation | 3.7042 | 26064.5258
salle_polyvalente_stephan_hessel | 2028 | none | salle_polyvalente_stephan_hessel_simulation_1 | floor_isolation | 4.5308 | 11928.917
salle_polyvalente_stephan_hessel | 2040 | salle_polyvalente_stephan_hessel_simulation_1 | salle_polyvalente_stephan_hessel_simulation_2 | indoor_wall_isolation | 0.9965 | 3738.2787
salle_polyvalente_stephan_hessel | 2046 | salle_polyvalente_stephan_hessel_simulation_2 | salle_polyvalente_stephan_hessel_simulation_7 | window_replacement_TG | 1.8587 | 67289.0174
stade_alain_mimoun | 2028 | none | stade_alain_mimoun_simulation_5 | indoor_wall_isolation, roof_isolation | 72.3934 | 123709.6
stade_alain_mimoun | 2031 | stade_alain_mimoun_simulation_5 | stade_alain_mimoun_simulation_10 | window_replacement_DG | 11.0436 | 134640
stade_municipal_des_bords_de_marne | 2027 | none | stade_municipal_des_bords_de_marne_simulation_1 | indoor_wall_isolation, VMC_installation | 55.367 | 166915.4161
stade_municipal_des_bords_de_marne | 2039 | stade_municipal_des_bords_de_marne_simulation_1 | stade_municipal_des_bords_de_marne_simulation_5 | roof_isolation | 33.7248 | 179793.7581
stade_municipal_des_bords_de_marne | 2043 | stade_municipal_des_bords_de_marne_simulation_5 | stade_municipal_des_bords_de_marne_simulation_10 | window_replacement_DG | 6.2393 | 194197.5835
stade_suzanne_lenglen | 2029 | none | stade_suzanne_lenglen_simulation_1 | indoor_wall_isolation | 10.1626 | 21960
stade_suzanne_lenglen | 2036 | stade_suzanne_lenglen_simulation_1 | stade_suzanne_lenglen_simulation_5 | roof_isolation | 7.9974 | 54879.06
stade_suzanne_lenglen | 2039 | stade_suzanne_lenglen_simulation_5 | stade_suzanne_lenglen_simulation_10 | window_replacement_DG | 8.0698 | 80520.04
tir_a_l'arc | 2035 | none | tir_a_l'arc_simulation_1 | indoor_wall_isolation | 5.422 | 37831.45
tir_a_l'arc | 2047 | tir_a_l'arc_simulation_1 | tir_a_l'arc_simulation_14 | window_replacement_DG, roof_isolation, VMC_installation | 8.225 | 374918.95
villa_cathala | 2026 | none | villa_cathala_simulation 4 | VMC_installation | 10.5246 | 21250
villa_cathala | 2028 | villa_cathala_simulation 4 | villa_cathala_simulation 8 | indoor_wall_isolation | 40.3507 | 48034.2
villa_cathala | 2049 | villa_cathala_simulation 8 | villa_cathala_simulation 10 | window_replacement_TG | 3.9528 | 216153.9

## timeline_renovations
building | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
abri_bouliste |  |  | abri_bouliste_simulation_1 | [10 empty] | abri_bouliste_simulation_2 | abri_bouliste_simulation_4 |  |  |  | abri_bouliste_simulation_11
accueil_de_loisirs_maternel_la_varenne | [17 empty] | accueil_de_loisirs_maternel_la_varenne_simulation_3 | [6 empty] | accueil_de_loisirs_maternel_la_varenne_simulation_14
association_31_rue_gambetta | [6 empty] | association_31_rue_gambetta_simulation_1 | [14 empty] | association_31_rue_gambetta_simulation_6
ateliers_municipaux_(ctm) | ateliers_municipaux_(ctm)_simulation_8 | [16 empty] | ateliers_municipaux_(ctm)_simulation_9
base_de_canoe_kayak |  |  | base_de_canoe_kayak_simulation_3 |  |  | base_de_canoe_kayak_simulation_12
bureaux_21_rue_des_sports | [6 empty] | bureaux_21_rue_des_sports_simulation_1 | [17 empty] | bureaux_21_rue_des_sports_simulation_14
cdj_du_champy | [12 empty] | cdj_du_champy_simulation_12 | cdj_du_champy_simulation_8
cdj_du_pave_neuf |  |  |  | cdj_du_pave_neuf_simulation_1 | [10 empty] | cdj_du_pave_neuf_simulation_3 | [8 empty] | cdj_du_pave_neuf_simulation_11
centre_aquatique_les_nymphéas | [6 empty] | centre_aquatique_les_nymphéas_simulation_1
centre_horticole | [14 empty] | centre_horticole_simulation_3 | [6 empty] | centre_horticole_simulation_7 | centre_horticole_simulation_15
cimetiere_nouveau | cimetiere_nouveau_simulation_1 | [8 empty] | cimetiere_nouveau_simulation_5 |  |  | cimetiere_nouveau_simulation_11
cinéma_le_bijou |  |  | cinéma_le_bijou_simulation_6 | [17 empty] | cinéma_le_bijou_simulation_7
club_ricardo_bofil | [16 empty] | club_ricardo_bofil_simulation_2
conservatoire_maurice_bacquet |  | conservatoire_maurice_bacquet_simulation 5 | [6 empty] | conservatoire_maurice_bacquet_simulation 8 | [14 empty] | conservatoire_maurice_bacquet_simulation 10
creche_multi_accueil_des_farfadets | [19 empty] | creche_multi_accueil_des_farfadets_simulation_1 |  |  | creche_multi_accueil_des_farfadets_simulation_2
crèche_et_halte_du_marnois | crèche_et_halte_du_marnois_simulation_1 | [12 empty] | crèche_et_halte_du_marnois_simulation_6 | [10 empty] | crèche_et_halte_du_marnois_simulation_10
crèche_familiale_du_champy_-_relais_des_assistances_maternelles |  | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_4 | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_3 | [8 empty] | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_6 |  |  | crèche_familiale_du_champy_-_relais_des_assistances_maternelles_simulation_7
crèche_petit_prince |  |  |  | crèche_petit_prince_simulation_3 | [14 empty] | crèche_petit_prince_simulation_7
crèche_robert_debré | crèche_robert_debré_simulation_8 | [21 empty] | crèche_robert_debré_simulation_9 | crèche_robert_debré_simulation_10
déchèterie_municipale |  |  | déchèterie_municipale_simulation_1 | [5 empty] | déchèterie_municipale_simulation_4 | [10 empty] | déchèterie_municipale_simulation_11
emaus_1_et__2 | [10 empty] | emaus_1_et__2_simulation_1 | [13 empty] | emaus_1_et__2_simulation_15
espace_michel_simon | [11 empty] | espace_michel_simon_simulation 4
groupe_scolaire_des_hauts_bâtons |  |  |  |  | groupe_scolaire_des_hauts_bâtons_simulation_7 | [13 empty] | groupe_scolaire_des_hauts_bâtons_simulation_9
groupe_scolaire_les_coteaux |  | groupe_scolaire_les_coteaux_simulation_13
groupe_scolaire_les_richardets |  |  |  | groupe_scolaire_les_richardets_simulation_1
groupe_scolaire_paul_serelle |  |  | groupe_scolaire_paul_serelle_simulation_1
groupe_scolaire_robert_desnos |  |  |  |  | groupe_scolaire_robert_desnos_simulation_7 | [17 empty] | groupe_scolaire_robert_desnos_simulation_10
gs_alex_dumas |  | gs_alex_dumas_simulation 3 | [7 empty] | gs_alex_dumas_simulation 10
gs_celestin_freinet |  |  |  | gs_celestin_freinet_simulation 2 | [8 empty] | gs_celestin_freinet_simulation 10
gs_clos_arche |  |  |  | gs_clos_arche_simulation 2 | [9 empty] | gs_clos_arche_simulation 10
gs_clos_dambert | [6 empty] | gs_clos_dambert_simulation 6 | [10 empty] | gs_clos_dambert_simulation 10
gs_george_brassens |  |  |  |  | gs_george_brassens_simulation 1 |  |  |  | gs_george_brassens_simulation 8
gs_joliot_curie |  |  |  | gs_joliot_curie_simulation 8 |  |  |  | gs_joliot_curie_simulation 9
gs_jules_ferry | [9 empty] | gs_jules_ferry_simulation 5 | [5 empty] | gs_jules_ferry_simulation 8 | [5 empty] | gs_jules_ferry_simulation 10
gs_jules_verne |  |  |  |  | gs_jules_verne_simulation 1 | [5 empty] | gs_jules_verne_simulation 8 |  |  | gs_jules_verne_simulation 10
gs_la_varenne | gs_la_varenne_simulation 5 | gs_la_varenne_simulation 7 | [18 empty] | gs_la_varenne_simulation 10
gs_les_abeilles |  |  | gs_les_abeilles_simulation 2 |  |  |  |  | gs_les_abeilles_simulation 10
gs_les_charmilles |  |  |  |  | gs_les_charmilles_simulation 1 |  |  |  | gs_les_charmilles_simulation 10
gs_les_noyers |  | gs_les_noyers_simulation 2 |  |  |  | gs_les_noyers_simulation 8 | [15 empty] | gs_les_noyers_simulation 10
gs_les_yvris |  |  | gs_les_yvris_simulation 1 | [11 empty] | gs_les_yvris_simulation 10
gs_van_gogh |  |  | gs_van_gogh_simulation 1 |  |  | gs_van_gogh_simulation 10
gymnase_champy |  |  |  |  | gymnase_champy_simulation 8 | [13 empty] | gymnase_champy_simulation 10
gymnase_de_la_butte_verte |  | gymnase_de_la_butte_verte_simulation_3 | [14 empty] | gymnase_de_la_butte_verte_simulation_8
gymnase_du_clos_de_l'arche | [19 empty] | gymnase_du_clos_de_l'arche_simulation_2
gymnase_la_varenne |  |  |  | gymnase_la_varenne_simulation 5 | [20 empty] | gymnase_la_varenne_simulation 10
gymnase_les_coteaux |  | gymnase_les_coteaux_simulation_1 | [15 empty] | gymnase_les_coteaux_simulation_9
gymnase_les_yvris | gymnase_les_yvris_simulation_1 | [5 empty] | gymnase_les_yvris_simulation_7 |  | gymnase_les_yvris_simulation_10
gymnase_louison_bobet | gymnase_louison_bobet_simulation 3 | [5 empty] | gymnase_louison_bobet_simulation 10
hangar_bleu |  |  | hangar_bleu_simulation_2 |  | hangar_bleu_simulation_3 | [5 empty] | hangar_bleu_simulation_9
local_associatif_pablo_picasso | [13 empty] | local_associatif_pablo_picasso_simulation_1 | [8 empty] | local_associatif_pablo_picasso_simulation_7
maison_de_la_jeunesse |  | maison_de_la_jeunesse_simulation_1 | [6 empty] | maison_de_la_jeunesse_simulation_9
maison_des_services_publics_-_pimms |  | maison_des_services_publics_-_pimms_simulation_1 | [10 empty] | maison_des_services_publics_-_pimms_simulation_2 |  |  |  | maison_des_services_publics_-_pimms_simulation_13
maison_des_syndicats | [19 empty] | maison_des_syndicats_simulation_1 |  |  | maison_des_syndicats_simulation_11
maison_medicale_du_champy | [22 empty] | maison_medicale_du_champy_simulation_8 | maison_medicale_du_champy_simulation_14
medecine_du_travail | [11 empty] | medecine_du_travail_simulation_3 | [11 empty] | medecine_du_travail_simulation_8
mille_club_des_yvris | [11 empty] | mille_club_des_yvris_simulation_8 |  |  | mille_club_des_yvris_simulation_4 | [9 empty] | mille_club_des_yvris_simulation_7
mpt_des_coteaux | [11 empty] | mpt_des_coteaux_simulation_8 | [8 empty] | mpt_des_coteaux_simulation_13
mpt_du_champy |  | mpt_du_champy_simulation_4 | [22 empty] | mpt_du_champy_simulation_10
mpt_jardin_des_sources_-_annexe_maison_pour_tous | [19 empty] | mpt_jardin_des_sources_-_annexe_maison_pour_tous_simulation_5
mpt_la_varenne |  |  | mpt_la_varenne_simulation 6 | [9 empty] | mpt_la_varenne_simulation 10
mpt_les_richardets | [14 empty] | mpt_les_richardets_simulation_5 |  | mpt_les_richardets_simulation_10
mpt_marcel_bou |  |  |  | mpt_marcel_bou_simulation 1 | [7 empty] | mpt_marcel_bou_simulation 9 |  |  | mpt_marcel_bou_simulation 10
multi_accueil_jean_piaget | [10 empty] | multi_accueil_jean_piaget_simulation_6 |  |  |  | multi_accueil_jean_piaget_simulation_7
noisy_connecte |  | noisy_connecte_simulation_3 |  | noisy_connecte_simulation_2 | [9 empty] | noisy_connecte_simulation_9
salle_de_boxe |  |  |  |  | salle_de_boxe_simulation_2 | [5 empty] | salle_de_boxe_simulation_5
salle_polyvalente_stephan_hessel |  |  | salle_polyvalente_stephan_hessel_simulation_1 | [11 empty] | salle_polyvalente_stephan_hessel_simulation_2 | [5 empty] | salle_polyvalente_stephan_hessel_simulation_7
stade_alain_mimoun |  |  | stade_alain_mimoun_simulation_5 |  |  | stade_alain_mimoun_simulation_10
stade_municipal_des_bords_de_marne |  | stade_municipal_des_bords_de_marne_simulation_1 | [11 empty] | stade_municipal_des_bords_de_marne_simulation_5 |  |  |  | stade_municipal_des_bords_de_marne_simulation_10
stade_suzanne_lenglen |  |  |  | stade_suzanne_lenglen_simulation_1 | [6 empty] | stade_suzanne_lenglen_simulation_5 |  |  | stade_suzanne_lenglen_simulation_10
tir_a_l'arc | [9 empty] | tir_a_l'arc_simulation_1 | [11 empty] | tir_a_l'arc_simulation_14
villa_cathala | villa_cathala_simulation 4 |  | villa_cathala_simulation 8 | [20 empty] | villa_cathala_simulation 10

## timeline_travaux
building | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
abri_bouliste |  |  | indoor_wall_isolation | [10 empty] | roof_isolation | floor_isolation |  |  |  | window_replacement_DG
accueil_de_loisirs_maternel_la_varenne | [17 empty] | roof_isolation | [6 empty] | indoor_wall_isolation, window_replacement_TG, floor_isolation
association_31_rue_gambetta | [6 empty] | indoor_wall_isolation | [14 empty] | window_replacement_DG, roof_isolation
ateliers_municipaux_(ctm) | exterior_wall_isolation, roof_isolation, VMC_installation, system_installation | [16 empty] | window_replacement_DG
base_de_canoe_kayak |  |  | indoor_wall_isolation, floor_isolation |  |  | roof_isolation
bureaux_21_rue_des_sports | [6 empty] | indoor_wall_isolation | [17 empty] | window_replacement_DG, roof_isolation
cdj_du_champy | [12 empty] | floor_isolation, VMC_installation | indoor_wall_isolation, roof_isolation
cdj_du_pave_neuf |  |  |  | indoor_wall_isolation | [10 empty] | roof_isolation | [8 empty] | floor_isolation, VMC_installation
centre_aquatique_les_nymphéas | [6 empty] | floor_isolation
centre_horticole | [14 empty] | exterior_wall_isolation | [6 empty] | roof_isolation | window_replacement_TG
cimetiere_nouveau | indoor_wall_isolation | [8 empty] | VMC_installation |  |  | floor_isolation, roof_isolation
cinéma_le_bijou |  |  | floor_isolation, system_installation | [17 empty] | window_replacement_TG
club_ricardo_bofil | [16 empty] | indoor_wall_isolation, floor_isolation
conservatoire_maurice_bacquet |  | system_installation | [6 empty] | indoor_wall_isolation, floor_isolation | [14 empty] | VMC_installation
creche_multi_accueil_des_farfadets | [19 empty] | indoor_wall_isolation |  |  | floor_isolation
crèche_et_halte_du_marnois | indoor_wall_isolation | [12 empty] | roof_isolation | [10 empty] | window_replacement_DG, VMC_installation
crèche_familiale_du_champy_-_relais_des_assistances_maternelles |  | VMC_installation | floor_isolation | [8 empty] | indoor_wall_isolation |  |  | window_replacement_DG
crèche_petit_prince |  |  |  | system_installation | [14 empty] | exterior_wall_isolation, window_replacement_TG
crèche_robert_debré | system_installation | [21 empty] | indoor_wall_isolation, roof_isolation, VMC_installation | window_replacement_DG
déchèterie_municipale |  |  | indoor_wall_isolation | [5 empty] | floor_isolation, roof_isolation | [10 empty] | VMC_installation
emaus_1_et__2 | [10 empty] | indoor_wall_isolation | [13 empty] | window_replacement_DG, floor_isolation, roof_isolation
espace_michel_simon | [11 empty] | window_replacement_DG
groupe_scolaire_des_hauts_bâtons |  |  |  |  | exterior_wall_isolation, roof_isolation, system_installation | [13 empty] | window_replacement_DG, VMC_installation
groupe_scolaire_les_coteaux |  | exterior_wall_isolation, roof_isolation
groupe_scolaire_les_richardets |  |  |  | exterior_wall_isolation, floor_isolation, roof_isolation, VMC_installation, system_installation
groupe_scolaire_paul_serelle |  |  | exterior_wall_isolation, floor_isolation, roof_isolation
groupe_scolaire_robert_desnos |  |  |  |  | indoor_wall_isolation, roof_isolation, system_installation | [17 empty] | window_replacement_DG, VMC_installation
gs_alex_dumas |  | system_installation | [7 empty] | exterior_wall_isolation, window_replacement_TG, VMC_installation
gs_celestin_freinet |  |  |  | indoor_wall_isolation | [8 empty] | window_replacement_DG, roof_isolation, VMC_installation
gs_clos_arche |  |  |  | indoor_wall_isolation | [9 empty] | window_replacement_DG, floor_isolation, VMC_installation, system_installation
gs_clos_dambert | [6 empty] | indoor_wall_isolation, VMC_installation | [10 empty] | window_replacement_DG
gs_george_brassens |  |  |  |  | exterior_wall_isolation |  |  |  | window_replacement_TG, floor_isolation, roof_isolation
gs_joliot_curie |  |  |  | exterior_wall_isolation, roof_isolation, system_installation |  |  |  | VMC_installation
gs_jules_ferry | [9 empty] | VMC_installation | [5 empty] | exterior_wall_isolation, window_replacement_TG | [5 empty] | floor_isolation, system_installation
gs_jules_verne |  |  |  |  | exterior_wall_isolation | [5 empty] | window_replacement_DG, floor_isolation |  |  | VMC_installation
gs_la_varenne | system_installation | exterior_wall_isolation, floor_isolation | [18 empty] | window_replacement_TG
gs_les_abeilles |  |  | exterior_wall_isolation |  |  |  |  | window_replacement_DG, roof_isolation, VMC_installation, system_installation
gs_les_charmilles |  |  |  |  | indoor_wall_isolation |  |  |  | window_replacement_DG, VMC_installation
gs_les_noyers |  | indoor_wall_isolation |  |  |  | roof_isolation, system_installation | [15 empty] | window_replacement_DG
gs_les_yvris |  |  | exterior_wall_isolation | [11 empty] | window_replacement_TG, VMC_installation
gs_van_gogh |  |  | exterior_wall_isolation |  |  | window_replacement_DG, roof_isolation, system_installation
gymnase_champy |  |  |  |  | VMC_installation, system_installation | [13 empty] | exterior_wall_isolation, window_replacement_TG
gymnase_de_la_butte_verte |  | system_installation | [14 empty] | window_replacement_DG, VMC_installation
gymnase_du_clos_de_l'arche | [19 empty] | window_replacement_TG
gymnase_la_varenne |  |  |  | VMC_installation | [20 empty] | window_replacement_DG, system_installation
gymnase_les_coteaux |  | indoor_wall_isolation | [15 empty] | window_replacement_DG, VMC_installation
gymnase_les_yvris | indoor_wall_isolation | [5 empty] | roof_isolation |  | VMC_installation, system_installation
gymnase_louison_bobet | VMC_installation | [5 empty] | exterior_wall_isolation, roof_isolation, system_installation
hangar_bleu |  |  | indoor_wall_isolation |  | system_installation | [5 empty] | floor_isolation, roof_isolation
local_associatif_pablo_picasso | [13 empty] | indoor_wall_isolation | [8 empty] | window_replacement_DG, floor_isolation
maison_de_la_jeunesse |  | indoor_wall_isolation | [6 empty] | floor_isolation, roof_isolation, VMC_installation
maison_des_services_publics_-_pimms |  | indoor_wall_isolation | [10 empty] | VMC_installation |  |  |  | window_replacement_DG, floor_isolation
maison_des_syndicats | [19 empty] | indoor_wall_isolation |  |  | window_replacement_TG, roof_isolation
maison_medicale_du_champy | [22 empty] | exterior_wall_isolation, floor_isolation, VMC_installation | window_replacement_DG
medecine_du_travail | [11 empty] | indoor_wall_isolation, VMC_installation | [11 empty] | floor_isolation, roof_isolation
mille_club_des_yvris | [11 empty] | floor_isolation |  |  | indoor_wall_isolation, roof_isolation | [9 empty] | window_replacement_DG
mpt_des_coteaux | [11 empty] | exterior_wall_isolation, floor_isolation, roof_isolation | [8 empty] | window_replacement_DG
mpt_du_champy |  | system_installation | [22 empty] | indoor_wall_isolation, window_replacement_TG, VMC_installation
mpt_jardin_des_sources_-_annexe_maison_pour_tous | [19 empty] | exterior_wall_isolation, window_replacement_TG, floor_isolation
mpt_la_varenne |  |  | VMC_installation | [9 empty] | indoor_wall_isolation, window_replacement_TG, roof_isolation, system_installation
mpt_les_richardets | [14 empty] | VMC_installation |  | indoor_wall_isolation, window_replacement_DG, roof_isolation
mpt_marcel_bou |  |  |  | indoor_wall_isolation | [7 empty] | floor_isolation, roof_isolation, system_installation |  |  | window_replacement_TG, VMC_installation
multi_accueil_jean_piaget | [10 empty] | indoor_wall_isolation, floor_isolation, VMC_installation |  |  |  | window_replacement_DG
noisy_connecte |  | floor_isolation |  | indoor_wall_isolation | [9 empty] | window_replacement_TG
salle_de_boxe |  |  |  |  | indoor_wall_isolation, floor_isolation | [5 empty] | VMC_installation
salle_polyvalente_stephan_hessel |  |  | floor_isolation | [11 empty] | indoor_wall_isolation | [5 empty] | window_replacement_TG
stade_alain_mimoun |  |  | indoor_wall_isolation, roof_isolation |  |  | window_replacement_DG
stade_municipal_des_bords_de_marne |  | indoor_wall_isolation, VMC_installation | [11 empty] | roof_isolation |  |  |  | window_replacement_DG
stade_suzanne_lenglen |  |  |  | indoor_wall_isolation | [6 empty] | roof_isolation |  |  | window_replacement_DG
tir_a_l'arc | [9 empty] | indoor_wall_isolation | [11 empty] | window_replacement_DG, roof_isolation, VMC_installation
villa_cathala | VMC_installation |  | indoor_wall_isolation | [20 empty] | window_replacement_TG

## stats_annees
year | renovations | gain_total | cost_total
2026 | 8 | 974.3777 | 1998051.7486
2027 | 13 | 1084.581 | 1998327.9924
2028 | 14 | 1152.3367 | 1998187.7233
2029 | 10 | 1332.5618 | 1998798.4922
2030 | 8 | 1009.2588 | 1999643.07
2031 | 4 | 333.2019 | 1998163.15
2032 | 6 | 338.0232 | 1998130.3438
2033 | 2 | 253.9696 | 1994397.645
2034 | 6 | 295.2971 | 1997482.3148
2035 | 4 | 270.5406 | 1997096.8125
2036 | 6 | 252.4833 | 1994054.0406
2037 | 6 | 397.5224 | 1997573.8477
2038 | 5 | 221.9017 | 1997323.5464
2039 | 9 | 281.1141 | 1998655.3732
2040 | 10 | 205.1022 | 1998311.4554
2041 | 1 | 106.2295 | 1977043.6665
2042 | 4 | 47.0593 | 1966054.3375
2043 | 5 | 47.8212 | 1930456.9056
2044 | 4 | 19.7014 | 1969599.3847
2045 | 5 | 27.4283 | 1849514.1683
2046 | 4 | 114.5598 | 1828343.8095
2047 | 5 | 84.6758 | 1718349.2241
2048 | 7 | -6.8421 | 1596391.1732
2049 | 6 | 78.7788 | 1068476.1667
2050 | 7 | 51.6431 | 1954903.3697